## UCP a
| UC title | Actors Weight | Transactions | UC Weight | UUCP
1 | Compose an order (customer) | 3 | 5 | 10 | 13
2 | Manage modify (customer) | 3 | 3 | 5 | 8
3 | Schedule appointment (customer) | 3 | 3 | 5 | 8
4 | Compose an order (employee) | 3 | 5 | 10 | 13
5 | Manage modify (employee) | 3 | 3 | 5 | 8
6 | Recharge virtual wallet (employee) | 3 | 3 | 5 | 8
7 | View pickup schedule (employee) | 3 | 2 | 5 | 8
8 | Register pickup (employee) | 3 | 4 | 10 | 13
9 | Register delivery (employee) | 3 | 4 | 10 | 13
10 | Confirm order ready to pick up (employee) | 3 | 3 | 5 | 8
11 | Insert products (farmer) | 3 | 3 | 5 | 8
12 | Confirm availability (farmer) | 3 | 3 | 5 | 8
13 | Modify availability (farmer) | 3 | 4 | 10 | 13 | Effort Computation | [5 empty] | Lookup tables
[12 empty] | Productivity Norms |  | Actor weights | Ratings
Factor | Description | Weight | Rating (0-5) | TF (W*R)
T1 | Distributed System | 2 | 5 | 10 |  | Context factors |  |  | Productivity norms |  |  | PN1 | 10 | 1 | 0
T2 | Response Time | 2 | 3 | 6 | [7 empty] | PN2 | 14 | 2 | 0.5
T3 | End User Efficiency | 1 | 4 | 4 |  | T Factor | 41.5 |  | n1 | 4 |  | PN3 | 18 | 3 | 1
T4 | Complex Internal Processing | 1 | 1 | 1 |  | TCF | 1.015 |  | n2 | 0 |  |  |  |  | 1.5
T5 | Reusable Code is a Focus | 1 | 2 | 2 |  |  |  |  | n1+n2 | 4 |  |  |  |  | 2
T6 | Easy to install | 0.5 | 4 | 2 |  | E Factor | 11.5 | [7 empty] | 2.5
T7 | Easy to use | 0.5 | 5 | 2.5 |  | ECF | 1.055 |  | Productivity | 14 | PH / UCP |  |  |  | 3
T8 | Cross-platform support | 2 | 5 | 10 | [10 empty] | 3.5
T9 | Easy to change | 1 | 0 | 0 |  | UUCP | 129 | [7 empty] | 4
T10 | Concurrent | 1 | 3 | 3 |  | UCP | 138.1364 | [7 empty] | 4.5
T11 | Includes Security Features | 1 | 1 | 1 | [10 empty] | 5
T12 | Provides Access for 3rd parties | 1 | 0 | 0 |  | Effort | 1933.9099 | person hours
T13 | User Training Required | 1 | 0 | 0 |  |  | equivalent to
[7 empty] | 241.7387 | person days |  | 6 | developers in the team
Factor | Description | Weight | Rating (0-5) | EF (W*R) | [5 empty] | 1 | projects in parallel
F1 | Familiarity With Project Domain | 1.5 | 0 | 0 |  | Person cost | 250 | €/day |  | 6 | FTE
F2 | Application Experience | 0.5 | 0 | 0 | [5 empty] | 40.2898 | calendar days
F3 | Object Oriented Experience | 1 | 5 | 5 |  | Total cost | 60434.6859 |  |  | 8.058 | weeks
F4 | Lead Analyst Capability | 0.5 | 1 | 0.5
F5 | Motivation | 1 | 4 | 4
F6 | Stable requirements | 2 | 1 | 2
F7 | Part Time Workers | -1 | 0 | 0
F8 | Difficulty of programming language | -1 | 0 | 0

## UCP b
| UC title | Actors Weight | Transactions | UC Weight | UUCP
1 | Compose an order (customer) | 3 | 5 | 10 | 13
2 | Manage modify (customer) | 3 | 3 | 5 | 8
3 | Schedule appointment (customer) | 3 | 3 | 5 | 8
4 | Compose an order (employee) | 3 | 5 | 10 | 13
5 | Manage modify (employee) | 3 | 3 | 5 | 8
6 | Recharge virtual wallet (employee) | 3 | 3 | 5 | 8
7 | View pickup schedule (employee) | 3 | 2 | 5 | 8
8 | Register pickup (employee) | 3 | 4 | 10 | 13
9 | Register delivery (employee) | 3 | 4 | 10 | 13
10 | Confirm order ready to pick up (employee) | 3 | 3 | 5 | 8
11 | Insert products (farmer) | 3 | 3 | 5 | 8
12 | Confirm availability (farmer) | 3 | 3 | 5 | 8
13 | Modify availability (farmer) | 3 | 4 | 10 | 13 | Effort Computation | [5 empty] | Lookup tables
[12 empty] | Productivity Norms |  | Actor weights | Ratings
Factor | Description | Weight | Rating (0-5) | TF (W*R)
T1 | Distributed System | 2 | 5 | 10 |  | Context factors |  |  | Productivity norms |  |  | PN1 | 10 | 1 | 0
T2 | Response Time | 2 | 3 | 6 | [7 empty] | PN2 | 14 | 2 | 0.5
T3 | End User Efficiency | 1 | 4 | 4 |  | T Factor | 41.5 |  | n1 | 2 |  | PN3 | 18 | 3 | 1
T4 | Complex Internal Processing | 1 | 1 | 1 |  | TCF | 1.015 |  | n2 | 1 |  |  |  |  | 1.5
T5 | Reusable Code is a Focus | 1 | 2 | 2 |  |  |  |  | n1+n2 | 3 |  |  |  |  | 2
T6 | Easy to install | 0.5 | 4 | 2 |  | E Factor | 16 | [7 empty] | 2.5
T7 | Easy to use | 0.5 | 5 | 2.5 |  | ECF | 0.92 |  | Productivity | 14 | PH / UCP |  |  |  | 3
T8 | Cross-platform support | 2 | 5 | 10 | [10 empty] | 3.5
T9 | Easy to change | 1 | 0 | 0 |  | UUCP | 129 | [7 empty] | 4
T10 | Concurrent | 1 | 3 | 3 |  | UCP | 120.4602 | [7 empty] | 4.5
T11 | Includes Security Features | 1 | 1 | 1 | [10 empty] | 5
T12 | Provides Access for 3rd parties | 1 | 0 | 0 |  | Effort | 1686.4428 | person hours
T13 | User Training Required | 1 | 0 | 0 |  |  | equivalent to
[7 empty] | 210.8053 | person days |  | 8 | developers in the team
Factor | Description | Weight | Rating (0-5) | EF (W*R) | [5 empty] | 5 | projects going on in the same time
F1 | Familiarity With Project Domain | 1.5 | 3 | 4.5 |  | Person cost | 100 | €/day |  | 1.6 | FTE
F2 | Application Experience | 0.5 | 0 | 0 | [5 empty] | 131.7533 | days of calendar
F3 | Object Oriented Experience | 1 | 3 | 3 |  | Total cost | 21080.535 |  |  | 26.3507 | weeks
F4 | Lead Analyst Capability | 0.5 | 5 | 2.5
F5 | Motivation | 1 | 1 | 1
F6 | Stable requirements | 2 | 5 | 10
F7 | Part Time Workers | -1 | 5 | -5
F8 | Difficulty of programming language | -1 | 0 | 0