## CF (hidden)
Timeline | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01
Net cash flow
INFLOWS
Sales revenue | 4.2029e+12 | 4.2029e+12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4837652.0356 | 4837652.0356 | 4837652.0356
Government subsidies / incentives
Joint venture funding
OUTFLOWS
CAPEX
Engineering | 1342464
Purchase process | [8 empty] | 2800 | 2240
Equipment and manufacturing | [9 empty] | #REF! |  |  | 871300 | 480 | 11000550 | 4401170
Transportation | [15 empty] | #REF! |  | #REF!
Total CAPEX | 1342464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2800 | #REF! | 0 | 0 | 871300 | 480 | 11000550 | #REF! | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OPEX
Overhead costs | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Production line setup costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295320 | 590640 | 664800 | 664800 | 666120 | 664800 | 369480 | 295320 | 172853.3333 | 24533.3333 | 24533.3333
OP.10 | [19 empty] | 74160 | 74160 | 74160 | 74160 | 74160
OP.20 | [18 empty] | 74160 | 74160 | 74160 | 74160 | 74160
OP.30 | [19 empty] | 147000 | 147000 | 147000
OP.40 | [19 empty] | 74160 | 74160 | 74160 | 74160 | 74160
OP.50 | [20 empty] | 74160 | 74160 | 74160 | 74160 | 74160
OP.60 | [18 empty] | 74160 | 74160 | 74160 | 74160 | 74160
OP.70 | [18 empty] | 147000 | 147000 | 147000
OP.80 | [21 empty] | 147000 | 147000 | 147000
OP.90 | [22 empty] | 74160 | 74160 | 74160 | 74160 | 74160
OP.100 | [23 empty] | 147000 | 147000 | 147000
OP.110 | [22 empty] | 74160 | 74160 | 74160 | 74160 | 74160
Final Line Testing | [26 empty] | 24533.3333 | 24533.3333 | 24533.3333
Contingency fund
Total OPEX
FV CF
DCF
NPV
PV

## Historical Financials
Economics (M€) |  |  |  | Cash flow (M€) |  |  |  | Indicators
| 2021 | 2022 | Change |  | 2022 | 2021 | Change |  | 2022 | 2021 | Change
Sales | 394 | 326 | -17.26% | Operating cash-flow |  |  |  | Return on Invested Capital
Cost of goods sold | 340 | 282 | -17.06% | Net income | 68 | 163 | -58.28% | ROI | 4,70% | 10,10% | -53%
Material | 246 | 197 | -19.92% | Items not involving current cash flows | 206 | 198 | 4.04% | Return on Equity
Direct labor | 28 | 25 | -10.71% | Changes in operating assets and liabilities | 54 | 35 | 54.29% | ROE | 7,00% | 15,50% | -55%
Overhead | 66 | 60 | -9.091% | Cash provided from operations | 328 | 396 | -17.17%
S.G.A. | 16 | 15 | -6.25% | Fixed asset additions | -115 | -144 | -20.14%
Selling | 9 | 8 | -11.11% | Increase in investments, other tangible, and intangible assets | -33 | -38 | -13.16%
General | 5 | 5 | 0% | Cash used for investing | -148 | -182 | -18.68%
Administrative | 2 | 2 | 0% | Net Cash-flow | 180 | 214 | -15.89%
EBITDA | 38 | 29 | -23.68%
% of Sales | 9.645% | 8.896%

## Price Calculations, Assumptions
Project 1 |  |  | Subtotal | Total | Assumptions
Direct costs | Start date | Finish date |  |  | Debt ratio | 80%
Phases |  |  |  |  | Equity ratio | 20%
Erection phase & Final line testing | 2025-01-01 | 2026-02-16 | 607030 |  | Joint Venture Magnus | 49%
Total |  |  |  | 607030 | Joint Venture GPC | 51%
Indirect costs
Engineering phase | 2024-01-15 | 2024-07-05 | 1342464 |  | corporate tax rate | 34%
Purchase phase | 2024-06-24 | 2024-07-15 | 5670
Manufacturing phase | 2024-07-12 | 2025-01-15 | 18686638 |  | Total CAPEX | 22796936.6
Transportation phase | 2024-07-12 | 2025-01-14 | 112550 |  | Equity Project 1 | 4559387.32
Total |  |  |  | 20147322 | Debt Project 1 | 18237549.28
Manufacturing line | Mon 24-01-15 | Tue 26-07-07 |  | 607030
Project 2 |  |  | Subtotal | Total |  | Duration projects (days)
Direct costs | Start date | Finish date | [5 empty] | Total
Phases |  |  |  |  | Total | 2023-11-02 | 2026-06-09
ERP Implementation | 2025-01-15 | 2026-07-03 | 248120
Meeting with stakeholders | 2026-07-03 | 2026-07-06 | 2000
Total | 2025-01-15 | 2026-07-06 |  | 250120 | Year 2023 | 2023-11-02 | 2023-12-31 | 59
[5 empty] | Year 2026 | 2026-01-01 | 2026-06-09 | 159
Price calculation |  |  | Subtotal | Total
Direct costs | Start date | Finish date
Project 1 | Mon 24-01-15 | Tue 26-07-07 | 607030
Project 2 | 2025-01-15 | 2026-07-06 | 250120
Total | Mon 24-01-15 | 2026-07-06 |  | 857150
Indirect costs
Total |  |  |  | 20147322
Overhead costs
Daily overhead costs |  |  | 5519.8142
Project duration | 2024-01-15 | 2026-07-07 | 646.45
Overhead costs |  |  |  | 3568283.9197
Contingency
Calculated CO
Interest on capital
Calculated IoC
Total project cost
Profit rate
X
Depreciation
Initial value of the machines | 18683200
Residual value is 30% | 5604960
Depreciation | 1307824
Formulas:
Finish date = [Finish date, row above]
Total = DAYS(K23,[Duration projects (days)])

## Data from MS project
WBS | Task Name | Start | Finish | Total Cost | Baseline | Variance | Actual | WBS | Task Name | Start | Finish | Cost
1 | Project | Mon 24-01-15 | Tue 26-07-07 | 24611812 | 0 | 4579375 | 0 | 1.2 | Project2 | 2025-01-15 | 2026-07-06 | 207682
1.1 | ENGINEERING PHASE | 2024-01-15 | 2024-07-05 | 1342464 | 0 | 632320 | 0 | 1.2.1 | ERP Implementation | 2025-01-15 | 2026-07-03 | 248120
1.1.1 | Detailed Engineering - Process | 2024-01-15 | 2024-07-05 | 918528 | 0 | 432640 | 0 | 1.2.1.1 | Prepare | 2025-01-15 | 2025-03-12 | 56256
1.1.1.1 | Detailed Engineering - Layout | 2024-01-15 | 2024-06-24 | 423936 | 0 | 199680 | 0 | 1.2.1.1.1 | Plan the meeting and revise requirements | 2025-01-15 | 2025-01-27 | 15040
1.1.1.2 | CIVIL WORKS REFURBISHMENT ERECTION PHASE | 2024-07-05 | 2025-03-05 | 840 | 0 | 0 | 0 | 1.2.1.1.2 | Develop projet plan | 2025-01-27 | 2025-02-06 | 6464
1.1.2 | Design Civil Works | 2024-07-05 | 2024-09-20 | 0 | 0 | 0 | 0 | 1.2.1.1.2.1 | Develop Project Charter | 2025-01-27 | 2025-01-29 | 1616
1.1.2.1 | Permits and Authorizations | 2024-08-16 | 2024-09-27 | 0 | 0 | 0 | 0 | 1.2.1.1.2.2 | Define project and quality management processes | 2025-01-29 | 2025-01-31 | 1616
1.1.2.2 | Site Installation | 2024-09-06 | 2024-09-27 | 0 | 0 | 0 | 0 | 1.2.1.1.2.3 | Create Master Plan | 2025-01-31 | 2025-02-04 | 1616
1.1.2.3 | Excavations & Foundations | 2024-09-27 | 2024-11-08 | 0 | 0 | 0 | 0 | 1.2.1.1.2.4 | Craft detailed work plan | 2025-02-04 | 2025-02-06 | 1616
1.1.2.4 | Structural Improvement | 2024-10-18 | 2024-12-06 | 0 | 0 | 0 | 0 | 1.2.1.1.3 | Validate and prioritize requirements | 2025-02-06 | 2025-02-18 | 6464
1.1.2.5 | Industrial Flooring | 2024-12-06 | 2025-01-24 | 0 | 0 | 0 | 0 | 1.2.1.1.4 | Establish governance and communicating strategy | 2025-02-18 | 2025-02-28 | 16000
1.1.2.6 | Finishes | 2025-01-10 | 2025-03-05 | 0 | 0 | 0 | 0 | 1.2.1.1.4.1 | Establish organizational structure | 2025-02-18 | 2025-02-21 | 6000
1.1.2.7 | Civil work final meeting | 2025-03-05 | 2025-03-06 | 840 | 0 | 2520 | 0 | 1.2.1.1.4.2 | Devise project tool strategy | 2025-02-21 | 2025-02-26 | 6000
1.1.2.8 | PURCHASE PROCESS (to repeat for each equipment type) | 2024-06-24 | 2024-07-15 | 5670 | 0 | 1400 | 0 | 1.2.1.1.4.3 | Assign resources to tasks | 2025-02-26 | 2025-02-28 | 4000
1.1.3 | Request for proposals | 2024-06-24 | 2024-06-26 | 2800 | 0 | 0 | 0 | 1.2.1.1.5 | Hire resources | 2025-02-28 | 2025-03-12 | 12288
1.1.3.1 | Waiting period | 2024-06-26 | 2024-07-10 | 0 | 0 | 1120 | 0 | 1.2.1.2 | Explore | 2025-03-12 | 2025-06-04 | 48080
1.1.3.2 | Competitive proposal analysis | 2024-07-10 | 2024-07-12 | 2240 | 0 | 0 | 0 | 1.2.1.2.1 | Perform AS IS analysis | 2025-03-12 | 2025-03-26 | 3040
1.1.3.3 | Orders | 2024-07-12 | 2024-07-15 | 630 | 0 | 0 | 0 | 1.2.1.2.2 | Perform FIT GAP analysis | 2025-03-26 | 2025-04-09 | 16040
1.1.3.4 | CNC Machine (Double and Single spindle) order | 2024-07-12 | 2024-07-12 | 70 | 0 | 0 | 0 | 1.2.1.2.3 | Perform TO BE analysis | 2025-04-09 | 2025-04-23 | 3040
1.1.3.4.1 | Drilling Machine order | 2024-07-12 | 2024-07-12 | 70 | 0 | 0 | 0 | 1.2.1.2.4 | Develop functional specification and realization plan | 2025-04-23 | 2025-05-07 | 6480
1.1.3.4.2 | Conveyors order (Powered and Overhead) | 2024-07-12 | 2024-07-12 | 70 | 0 | 0 | 0 | 1.2.1.2.5 | Develop security, privacy and controls approach | 2025-05-07 | 2025-05-21 | 3440
1.1.3.4.3 | Washing station (Final and Intermidiate) order | 2024-07-12 | 2024-07-12 | 70 | 0 | 0 | 0 | 1.2.1.2.6 | Develop Business Process Blueprints | 2025-05-21 | 2025-06-04 | 16040
1.1.3.4.4 | Assembly Station order | 2024-07-12 | 2024-07-12 | 70 | 0 | 0 | 0 | 1.2.1.3 | Build | 2025-06-04 | 2025-10-22 | 56880
1.1.3.4.5 | Gantry Loader order | 2024-07-12 | 2024-07-12 | 70 | 0 | 0 | 0 | 1.2.1.3.1 | Develop technical specifications | 2025-06-04 | 2025-07-02 | 16320
1.1.3.4.6 | Rotating Table | 2024-07-12 | 2024-07-12 | 70 | 0 | 0 | 0 | 1.2.1.3.2 | Develop configuration and code | 2025-07-02 | 2025-07-30 | 8080
1.1.3.4.7 | Lift/Lower Components | 2024-07-12 | 2024-07-12 | 70 | 0 | 0 | 0 | 1.2.1.3.3 | Perform unit test | 2025-07-30 | 2025-08-27 | 8080
1.1.3.4.8 | Manipulator | 2024-07-12 | 2024-07-15 | 70 |  |  |  | 1.2.1.3.4 | Develop learning documentation | 2025-08-27 | 2025-09-24 | 8080
1.4 | EQUIPMENT MANUFACTURING PHASE (values for each unit of equipment) | 2024-07-12 | 2025-01-15 | 18686638 |  |  |  | 1.2.1.3.5 | Develop Go/No Go criteria and deployment plan | 2025-09-24 | 2025-10-22 | 16320
1.4.1 | Single Spindle machine | 2024-07-12 | 2024-12-16 | 1020550 |  |  |  | 1.2.1.4 | Test | 2026-02-17 | 2026-04-03 | 19224
1.4.1.1 | Single Spindle Machine | 2024-07-12 | 2024-12-13 | 1020000 |  |  |  | 1.2.1.4.1 | Conduct integration test | 2026-02-17 | 2026-02-25 | 2424
1.4.1.2 | Technical requiremets check | 2024-12-13 | 2024-12-16 | 480 |  |  |  | 1.2.1.4.2 | Conduct mock data conversion | 2026-02-25 | 2026-03-05 | 2424
1.4.1.3 | Payment | 2024-12-16 | 2024-12-16 | 70 |  |  |  | 1.2.1.4.3 | Develop a transition plan | 2026-03-05 | 2026-03-10 | 4992
1.4.2 | Double Spindle Machine | 2024-07-12 | 2024-12-16 | 11000550 |  |  |  | 1.2.1.4.4 | Prepare for user acceptance test | 2026-03-10 | 2026-03-26 | 3648
1.4.2.1 | Double Spindle machine | 2024-07-12 | 2024-12-13 | 11000000 |  |  |  | 1.2.1.4.5 | Conduct acceptance test | 2026-03-26 | 2026-04-03 | 5736
1.4.2.2 | Technical requiremets check | 2024-12-13 | 2024-12-16 | 480 |  |  |  | 1.2.1.5 | Deploy | 2026-04-03 | 2026-05-08 | 11178
1.4.2.3 | Payment | 2024-12-16 | 2024-12-16 | 70 |  |  |  | 1.2.1.5.1 | Meeting to start project 3 | 2026-04-03 | 2026-04-06 | 1906
1.4.3 | Drilling machine | 2024-07-12 | 2024-10-15 | 270550 |  |  |  | 1.2.1.5.2 | Deploy learning to end-users | 2026-04-06 | 2026-04-20 | 600
1.4.3.1 | Drilling machine | 2024-07-12 | 2024-10-14 | 270000 |  |  |  | 1.2.1.5.3 | Conduct deployment Go/No Go decision set | 2026-04-20 | 2026-04-27 | 2060
1.4.3.2 | Technical requiremets check | 2024-10-14 | 2024-10-15 | 480 |  |  |  | 1.2.1.5.4 | Execute production deployment | 2026-04-27 | 2026-05-01 | 3072
1.4.3.3 | Payment | 2024-10-15 | 2024-10-15 | 70 |  |  |  | 1.2.1.5.5 | Execute final data migration | 2026-05-01 | 2026-05-08 | 3540
1.4.4 | Powered Conveyors | 2024-07-12 | 2025-01-13 | 250550 |  |  |  | 1.2.1.6 | Run | 2026-05-08 | 2026-07-03 | 22640
1.4.4.1 | Powered conveyors | 2024-07-12 | 2025-01-10 | 250000 |  |  |  | 1.2.1.6.1 | Develop post implementation and evaluation reports | 2026-05-08 | 2026-05-22 | 3640
1.4.4.2 | Technical requiremets check | 2025-01-10 | 2025-01-13 | 480 |  |  |  | 1.2.1.6.2 | Conduct service delivery transition | 2026-05-22 | 2026-06-05 | 7680
1.4.4.3 | Payment | 2025-01-13 | 2025-01-13 | 70 |  |  |  | 1.2.1.6.3 | Track value realization | 2026-06-05 | 2026-06-19 | 3640
1.4.5 | Overhead Conveyors | 2024-07-12 | 2025-01-13 | 70750 |  |  |  | 1.2.1.6.4 | Close project | 2026-06-19 | 2026-07-03 | 7680
1.4.5.1 | Overhead Conveyors | 2024-07-12 | 2025-01-10 | 70200 |  |  |  | 1.2.2 | Meeting with Stakeholders for project 2 closure | 2026-07-03 | 2026-07-06 | 2000
1.4.5.2 | Technical requiremets check | 2025-01-10 | 2025-01-13 | 480
1.4.5.3 | Payment | 2025-01-13 | 2025-01-13 | 70
1.4.6 | Intermidiate Washing stations | 2024-07-12 | 2024-10-21 | 530550
1.4.6.1 | Intermidiate Washing stations | 2024-07-12 | 2024-10-18 | 530000
1.4.6.2 | Technical requiremets check | 2024-10-18 | 2024-10-21 | 480
1.4.6.3 | Payment | 2024-10-21 | 2024-10-21 | 70
1.4.7 | Final Washing station | 2024-07-12 | 2024-10-21 | 970550
1.4.7.1 | Final Washing station | 2024-07-12 | 2024-10-18 | 970000
1.4.7.2 | Technical requiremets check | 2024-10-18 | 2024-10-21 | 480
1.4.7.3 | Payment | 2024-10-21 | 2024-10-21 | 70
1.4.8 | Assembly station | 2024-07-12 | 2024-12-03 | 2200550
1.4.8.1 | Assembly station | 2024-07-12 | 2024-11-29 | 2200000
1.4.8.2 | Technical requiremets check | 2024-11-29 | 2024-12-02 | 480
1.4.8.3 | Payment | 2024-12-02 | 2024-12-03 | 70
1.4.9 | Gantry loaders | 2024-07-12 | 2024-11-26 | 2200550
1.4.9.1 | Gantry loaders | 2024-07-12 | 2024-11-22 | 2200000
1.4.9.2 | Technical requiremets check | 2024-11-22 | 2024-11-25 | 480
1.4.9.3 | Payment | 2024-11-25 | 2024-11-26 | 70 | 0 | 253675 | 0
1.4.10 | Rotating Table | 2024-07-12 | 2025-01-14 | 112550 | 0 | 62500 | 0
1.4.10.1 | Rotating Table | 2024-07-12 | 2025-01-10 | 112000 | 0 | 62500 | 0
1.4.10.2 | Technical requiremets check | 2025-01-10 | 2025-01-13 | 480 | 0 | 55000 | 0
1.4.10.3 | Payment | 2025-01-13 | 2025-01-14 | 70 | 0 | 7500 | 0
1.4.11 | Lift/Lower Components | 2024-07-12 | 2025-01-14 | 32950 | 0 | 975 | 0
1.4.11.1 | Lift/Lower Components | 2024-07-12 | 2025-01-10 | 32400 | 0 | 1000 | 0
1.4.11.2 | Technical requiremets check | 2025-01-10 | 2025-01-13 | 480 | 0 | 31250 | 0
1.4.11.3 | Payment | 2025-01-13 | 2025-01-14 | 70 | 0 | 2450 | 0
1.4.12 | Manipulator | 2024-07-15 | 2025-01-14 | 22550 | 0 | 1000 | 0
1.4.12.1 | Manipulator | 2024-07-15 | 2025-01-13 | 22000 | 0 | 14000 | 0
1.4.12.2 | Technical requiremets check | 2025-01-13 | 2025-01-14 | 480 | 0 | 14000 | 0
1.4.12.3 | Payment | 2025-01-14 | 2025-01-14 | 70 | 0 | 1500 | 0
1.1.4.13 | Meeting to start project 2 & 3 | 2025-01-14 | 2025-01-15 | 3438
1.1.4.13.1 | Meeting to start project 2 | 2025-01-14 | 2025-01-14 | 1280
1.1.4.13.2 | Meeting to start project 3 | 2025-01-14 | 2025-01-15 | 2158
1.1.5 | TRANSPORTATION PHASE (from the contractor to the owner's construction site) | 2024-10-15 | 2025-04-08 | 143000
1.1.5.1 | Single Spindle Machine | 2024-12-16 | 2025-03-10 | 10000
1.1.5.2 | Double Spindle Machine | 2024-12-16 | 2025-03-10 | 55000
1.1.5.3 | Drilling Machine | 2024-10-15 | 2025-01-07 | 5000
1.1.5.4 | Powered Conveyors | 2025-01-13 | 2025-02-03 | 7500
1.1.5.5 | Overhead Conveyors | 2025-01-13 | 2025-02-03 | 1500
1.1.5.6 | Manipulator | 2025-01-14 | 2025-04-08 | 5000
1.1.5.7 | Gantry Loader | 2024-11-26 | 2025-02-18 | 35000
1.1.5.8 | Rotating table | 2025-01-14 | 2025-03-18 | 3500
1.1.5.9 | Lift/Lower Components | 2025-01-14 | 2025-04-08 | 5000
1.1.5.10 | Intermidiate washing station | 2024-10-30 | 2025-01-01 | 7000
1.1.5.11 | Final washing station | 2024-10-30 | 2025-01-01 | 7000
1.1.5.12 | Assembly station | 2024-12-11 | 2025-01-01 | 1500
1.6 | ON SITE ERECTION PHASE | 2025-01-01 | 2026-01-20 | 4359600 | 0 | 123600 | 0
1.6.1 | OP.10 | 2025-03-10 | 2025-07-14 | 370800 | 0 | 61800 | 0
1.6.1.1 | Single-spindle cnc machine 1 | 2025-03-10 | 2025-05-12 | 185400 | 0 | 23400 | 0
1.6.1.1.1 | Installation | 2025-03-10 | 2025-05-12 | 70200 | 0 | 12800 | 0
1.6.1.1.2 | Electrical&IT Connections | 2025-03-10 | 2025-03-17 | 38400 | 0 | 25600 | 0
1.6.1.1.3 | Final Assembly | 2025-03-17 | 2025-03-31 | 76800 | 0 | 61800 | 0
1.6.1.2 | Single-spindle cnc machine 2 | 2025-05-12 | 2025-07-14 | 185400 | 0 | 23400 | 0
1.6.1.2.1 | Installation | 2025-05-12 | 2025-07-14 | 70200 | 0 | 12800 | 0
1.6.1.2.2 | Electrical&IT Connections | 2025-05-12 | 2025-05-19 | 38400 | 0 | 25600 | 0
1.6.1.2.3 | Final Assembly | 2025-05-19 | 2025-06-02 | 76800 | 0 | 123600 | 0
1.6.2 | OP.20 | 2025-01-07 | 2025-05-13 | 370800 | 0 | 123600 | 0
1.6.2.1 | Drilling machine | 2025-01-07 | 2025-05-13 | 370800 | 0 | 46800 | 0
1.6.2.1.1 | Installation | 2025-01-07 | 2025-05-13 | 140400 | 0 | 25600 | 0
1.6.2.1.2 | Electrical&IT Connections | 2025-01-07 | 2025-01-21 | 76800 | 0 | 51200 | 0
1.6.2.1.3 | Final Assembly | 2025-01-21 | 2025-02-18 | 153600 | 0 | 147000 | 0
1.6.3 | OP.30 | 2025-05-13 | 2025-07-15 | 441000 | 0 | 73500 | 0
1.6.3.1 | Double-spindle CNC machine 1 | 2025-05-13 | 2025-06-13 | 220500 | 0 | 35100 | 0
1.6.3.1.1 | Installation | 2025-05-13 | 2025-06-13 | 105300 | 0 | 12800 | 0
1.6.3.1.2 | Electrical&IT Connections | 2025-05-13 | 2025-05-20 | 38400 | 0 | 25600 | 0
1.6.3.1.3 | Final Assembly | 2025-05-20 | 2025-06-03 | 76800 | 0 | 73500 | 0
1.6.3.2 | Double-spindle CNC machine 2 | 2025-06-13 | 2025-07-15 | 220500 | 0 | 35100 | 0
1.6.3.2.1 | Installation | 2025-06-13 | 2025-07-15 | 105300 | 0 | 12800 | 0
1.6.3.2.2 | Electrical&IT Connections | 2025-06-13 | 2025-06-20 | 38400 | 0 | 25600 | 0
1.6.3.2.3 | Final Assembly | 2025-06-20 | 2025-07-04 | 76800 | 0 | 123600 | 0
1.6.4 | OP.40 | 2025-05-07 | 2025-09-10 | 370800 | 0 | 61800 | 0
1.6.4.1 | Double-spindle CNC machine 3 | 2025-05-07 | 2025-07-09 | 185400 | 0 | 23400 | 0
1.6.4.1.1 | Installation | 2025-05-07 | 2025-07-09 | 70200 | 0 | 12800 | 0
1.6.4.1.2 | Electrical&IT Connections | 2025-05-07 | 2025-05-14 | 38400 | 0 | 25600 | 0
1.6.4.1.3 | Final Assembly | 2025-05-14 | 2025-05-28 | 76800 | 0 | 61800 | 0
1.6.4.2 | Double-spindle CNC machine 4 | 2025-07-09 | 2025-09-10 | 185400 | 0 | 23400 | 0
1.6.4.2.1 | Installation | 2025-07-09 | 2025-09-10 | 70200 | 0 | 12800 | 0
1.6.4.2.2 | Electrical&IT Connections | 2025-07-09 | 2025-07-16 | 38400 | 0 | 25600 | 0
1.6.4.2.3 | Final Assembly | 2025-07-16 | 2025-07-30 | 76800 | 0 | 123600 | 0
1.6.5 | OP.50 | 2025-07-14 | 2025-11-17 | 370800 | 0 | 41200 | 0
1.6.5.1 | Double-spindle CNC machine 5 | 2025-07-14 | 2025-08-25 | 123600 | 0 | 15600 | 0
1.6.5.1.1 | Installation | 2025-07-14 | 2025-08-25 | 46800 | 0 | 8524.8 | 0
1.6.5.1.2 | Electrical&IT Connections | 2025-07-14 | 2025-07-18 | 25574.4 | 0 | 17075.2 | 0
1.6.5.1.3 | Final Assembly | 2025-07-18 | 2025-07-28 | 51225.6 | 0 | 41200 | 0
1.6.5.2 | Double-spindle CNC machine 6 | 2025-08-25 | 2025-10-06 | 123600 | 0 | 15600 | 0
1.6.5.2.1 | Installation | 2025-08-25 | 2025-10-06 | 46800 | 0 | 8524.8 | 0
1.6.5.2.2 | Electrical&IT Connections | 2025-08-25 | 2025-08-29 | 25574.4 | 0 | 17075.2 | 0
1.6.5.2.3 | Final Assembly | 2025-08-29 | 2025-09-08 | 51225.6 | 0 | 41200 | 0
1.6.5.3 | Single-spindle cnc machine 3 | 2025-10-06 | 2025-11-17 | 123600 | 0 | 15600 | 0
1.6.5.3.1 | Installation | 2025-10-06 | 2025-11-17 | 46800 | 0 | 8524.8 | 0
1.6.5.3.2 | Electrical&IT Connections | 2025-10-06 | 2025-10-10 | 25574.4 | 0 | 17075.2 | 0
1.6.5.3.3 | Final Assembly | 2025-10-10 | 2025-10-20 | 51225.6 | 0 | 123600 | 0
1.6.6 | OP.60 | 2025-01-01 | 2025-05-07 | 370800 | 0 | 123600 | 0
1.6.6.1 | Intermediate washing station | 2025-01-01 | 2025-05-07 | 370800 | 0 | 46800 | 0
1.6.6.1.1 | Installation | 2025-01-01 | 2025-05-07 | 140400 | 0 | 25600 | 0
1.6.6.1.2 | Electrical&IT Connections | 2025-01-01 | 2025-01-15 | 76800 | 0 | 51200 | 0
1.6.6.1.3 | Final Assembly | 2025-01-15 | 2025-02-12 | 153600 | 0 | 147000 | 0
1.6.7 | OP.70 | 2025-01-01 | 2025-03-05 | 441000 | 0 | 147000 | 0
1.6.7.1 | Valve guides assembly station | 2025-01-01 | 2025-03-05 | 441000 | 0 | 70200 | 0
1.6.7.1.1 | Installation | 2025-01-01 | 2025-03-05 | 210600 | 0 | 25600 | 0
1.6.7.1.2 | Electrical&IT Connections | 2025-01-01 | 2025-01-15 | 76800 | 0 | 51200 | 0
1.6.7.1.3 | Final Assembly | 2025-01-15 | 2025-02-12 | 153600 | 0 | 147000 | 0
1.6.8 | OP.80 | 2025-07-15 | 2025-09-16 | 441000 | 0 | 147000 | 0
1.6.8.1 | Double-spindle CNC machine 7 | 2025-07-15 | 2025-08-15 | 220500 | 0 | 35100 | 0
1.6.8.1.1 | Installation | 2025-07-15 | 2025-08-15 | 105300 | 0 | 12800 | 0
1.6.8.1.2 | Electrical&IT Connections | 2025-07-15 | 2025-07-22 | 38400 | 0 | 25600 | 0
1.6.8.1.3 | Final Assembly | 2025-07-22 | 2025-08-05 | 76800 | 0 | 73500 | 0
1.6.8.1.4 | Double-spindle CNC machine 8 | 2025-08-15 | 2025-09-16 | 220500 | 0 | 35100 | 0
1.6.8.1.4.1 | Installation | 2025-08-15 | 2025-09-16 | 105300 | 0 | 12800 | 0
1.6.8.1.4.2 | Electrical&IT Connections | 2025-08-15 | 2025-08-22 | 38400 | 0 | 25600 | 0
1.6.8.1.4.3 | Final Assembly | 2025-08-22 | 2025-09-05 | 76800 | 0 | 123600 | 0
1.6.9 | OP.90 | 2025-09-10 | 2026-01-14 | 370800 | 0 | 123600 | 0
1.6.9.1 | Double-Spindle CNC machine 9 | 2025-09-10 | 2025-10-22 | 123600 | 0 | 15600 | 0
1.6.9.1.1 | Installation | 2025-09-10 | 2025-10-22 | 46800 | 0 | 8524.8 | 0
1.6.9.1.2 | Electrical&IT Connections | 2025-09-10 | 2025-09-15 | 25574.4 | 0 | 17075.2 | 0
1.6.9.1.3 | Final Assembly | 2025-09-15 | 2025-09-24 | 51225.6 | 0 | 41200 | 0
1.6.9.1.4 | Double-Spindle CNC machine 10 | 2025-10-22 | 2025-12-03 | 123600 | 0 | 15600 | 0
1.6.9.1.4.1 | Installation | 2025-10-22 | 2025-12-03 | 46800 | 0 | 8524.8 | 0
1.6.9.1.4.2 | Electrical&IT Connections | 2025-10-22 | 2025-10-27 | 25574.4 | 0 | 17075.2 | 0
1.6.9.1.4.3 | Final Assembly | 2025-10-27 | 2025-11-05 | 51225.6 | 0 | 41200 | 0
1.6.9.1.5 | Double-Spindle CNC machine 11 | 2025-12-03 | 2026-01-14 | 123600 | 0 | 15600 | 0
1.6.9.1.5.1 | Installation | 2025-12-03 | 2026-01-14 | 46800 | 0 | 8524.8 | 0
1.6.9.1.5.2 | Electrical&IT Connections | 2025-12-03 | 2025-12-08 | 25574.4 | 0 | 17075.2 | 0
1.6.9.1.5.3 | Final Assembly | 2025-12-08 | 2025-12-17 | 51225.6 | 0 | 147000 | 0
1.6.10 | OP.100 | 2025-11-17 | 2026-01-19 | 441000 | 0 | 147000 | 0
1.6.10.1 | Final washing station | 2025-11-17 | 2026-01-19 | 441000 | 0 | 70200 | 0
1.6.10.1.1 | Installation | 2025-11-17 | 2026-01-19 | 210600 | 0 | 25600 | 0
1.6.10.1.2 | Electrical&IT Connections | 2025-11-17 | 2025-12-01 | 76800 | 0 | 51200 | 0
1.6.10.1.3 | Final Assembly | 2025-12-01 | 2025-12-29 | 153600 | 0 | 123600 | 0
1.6.11 | OP.110 | 2025-09-16 | 2026-01-20 | 370800 | 0 | 123600 | 0
1.6.11.1 | Final assembly station | 2025-09-16 | 2026-01-20 | 370800 | 0 | 46800 | 0
1.6.11.1.1 | Installation | 2025-09-16 | 2026-01-20 | 140400 | 0 | 25600 | 0
1.6.11.1.2 | Electrical&IT Connections | 2025-09-16 | 2025-09-30 | 76800 | 0 | 51200 | 0
1.6.11.1.3 | Final Assembly | 2025-09-30 | 2025-10-28 | 153600 | 0 | 147200 | 0
1.7 | FINAL LINE TESTING | 2026-01-20 | 2026-02-16 | 73600 | 0 | 147200 | 0
1.7.1 | Testing | 2026-01-20 | 2026-02-17 | 73600

## CF (2) (hidden)
Timeline | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01 | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01
Net cash flow
INFLOWS
Sales revenue | 4.2029e+12 | 4.2029e+12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4837652.0356 | 4837652.0356 | 4837652.0356
Government subsidies / incentives
Joint venture funding
OUTFLOWS
OPEX
Overhead costs | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
Production line setup costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 295320 | 590640 | 664800 | 664800 | 666120 | 664800 | 369480 | 295320 | 172853.3333 | 24533.3333 | 24533.3333
OP.10 | [19 empty] | 74160 | 74160 | 74160 | 74160 | 74160
OP.20 | [18 empty] | 74160 | 74160 | 74160 | 74160 | 74160
OP.30 | [19 empty] | 147000 | 147000 | 147000
OP.40 | [19 empty] | 74160 | 74160 | 74160 | 74160 | 74160
OP.50 | [20 empty] | 74160 | 74160 | 74160 | 74160 | 74160
OP.60 | [18 empty] | 74160 | 74160 | 74160 | 74160 | 74160
OP.70 | [18 empty] | 147000 | 147000 | 147000
OP.80 | [21 empty] | 147000 | 147000 | 147000
OP.90 | [22 empty] | 74160 | 74160 | 74160 | 74160 | 74160
OP.100 | [23 empty] | 147000 | 147000 | 147000
OP.110 | [22 empty] | 74160 | 74160 | 74160 | 74160 | 74160
Final Line Testing | [26 empty] | 24533.3333 | 24533.3333 | 24533.3333
Contingency fund
Total OPEX
EBITD
Depreciation
EBIT
Tax expense
EBI(AT)
CAPEX
Engineering | 1342464
Purchase process | [8 empty] | 2800 | 2240
Equipment and manufacturing | [9 empty] | #REF! |  |  | 871300 | 480 | 11000550 | 4401170
Transportation | [15 empty] | #REF! |  | #REF!
Total CAPEX | 1342464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2800 | #REF! | 0 | 0 | 871300 | 480 | 11000550 | #REF! | 0 | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cash flow
Cash Flow
Cumulative Cash Flow
DSCR
Average
Profitability
Cost of equity
NPV
IRR
Debt ratio
Debt amount
DSCR Rarget
Annual payment
Equity
Levered profitability
WACC
Cd
Ce levered
NPV WACC

## Cash flow
Timeline | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
Year | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034
Net cash flow
INFLOWS
Bank loan |  | 10000000
Sales revenue |  | 0 | 0 | 7643490.2163 | 11924309.152 | 16067154.846 | 20580240.1183 | 25489562.8519 | 30822763.6948 | 36609223.8657 | 42880168.5656 | 49668776.3048
Government subsidies / incentives
Joint venture funding
Sum of INFLOWS |  | 10000000 | 0 | 7643490.2163 | 11924309.152 | 16067154.846 | 20580240.1183 | 25489562.8519 | 30822763.6948 | 36609223.8657 | 42880168.5656 | 49668776.3048
OUTFLOWS
OPEX | [5 empty] | See sheet "Revenue" for information about the revenues
Overhead costs |  | 2014732.2 | 2014732.2 | 877650.4652 |  | Please see below in the cash flow sheet (Wacc, NPV, debt amount, interests, equity to use etc.,)
Production line setup costs |  |  | 4286000 | 73600
ERP Implementation |  |  | 202904 | 33818
Interests |  |  |  | 65452.0062 | 65452.0062 | 65452.0062 | 65452.0062 | 65452.0062 | 65452.0062 | 65452.0062 | 65452.0062 | 65452.0062
Annual debt payment without interest |  |  |  | 1451263.9958 | 1451263.9958 | 1451263.9958 | 1451263.9958 | 1451263.9958 | 1451263.9958 | 1451263.9958 | 1451263.9958 | 1451263.9958
Total Annual debt payment |  |  |  | 1516716.002 | 1516716.002 | 1516716.002 | 1516716.002 | 1516716.002 | 1516716.002 | 1516716.002 | 1516716.002 | 1516716.002
Total OPEX |  | 2014732.2 | 6503636.2 | 4018500.4692 | 3033432.004 | 3033432.004 | 3033432.004 | 3033432.004 | 3033432.004 | 3033432.004 | 3033432.004 | 3033432.004
EBITD |  | 7985267.8 | -6503636.2 | 3624989.7471 | 8890877.148 | 13033722.842 | 17546808.1143 | 22456130.8479 | 27789331.6908 | 33575791.8618 | 39846736.5616 | 46635344.3008
Depreciation |  | 1307824 | 1307824 | 1307824 | 1307824 | 1307824 | 1307824 | 1307824 | 1307824 | 1307824 | 1307824 | 1307824
EBIT |  | 6677443.8 | -7811460.2 | 2317165.7471 | 7583053.148 | 11725898.842 | 16238984.1143 | 21148306.8479 | 26481507.6908 | 32267967.8618 | 38538912.5616 | 45327520.3008
Tax expense |  | 2270330.892 | -2655896.468 | 787836.354 | 2578238.0703 | 3986805.6063 | 5521254.5989 | 7190424.3283 | 9003712.6149 | 10971109.073 | 13103230.2709 | 15411356.9023
EBI(AT) |  | 4407112.908 | -5155563.732 | 1529329.3931 | 5004815.0777 | 7739093.2357 | 10717729.5154 | 13957882.5196 | 17477795.0759 | 21296858.7888 | 25435682.2907 | 29916163.3985
CAPEX
Engineering |  | 1342464
Purchase process |  | 5670
Equipment manufacturing |  | 18686638
Transportation |  |  | 143000
Contingency Fund |  | 2619164.6
Total CAPEX |  | 22653936.6 | 143000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Net Cash Flow |  | -16938999.692 | -3990739.732 | 2837153.3931 | 6312639.0777 | 9046917.2357 | 12025553.5154 | 15265706.5196 | 18785619.0759 | 22604682.7888 | 26743506.2907 | 31223987.3985
Free Cash Flow |  | -18246823.692 | -5298563.732 | 1529329.3931 | 5004815.0777 | 7739093.2357 | 10717729.5154 | 13957882.5196 | 17477795.0759 | 21296858.7888 | 25435682.2907 | 29916163.3985
Cumulative Free Cash Flow |  | -23545387.424 | -3769234.3389 | 6534144.4708 | 12743908.3134 | 18456822.7511 | 24675612.0351 | 31435677.5956 | 38774653.8647 | 46732541.0794 | 55351845.6892
Net Cash Flow to repay the CAPEX |  | -16938999.692 | -1955462.4687 | 1390205.1626 | 3093193.1481 | 4432989.4455 | 5892521.2226 | 7480196.1946 | 9204953.3472 | 11076294.5665 | 13104318.0824 | 15299753.8253
1. Profitability without debt
NPV | 11021390.6085
Cost of equity | 13%
IRR | 34.82%
In this step NPV was computed just to show the advantages in terms of NPV if we use debt to finance the project
2. Choosing debt amount
Amount of debt choosen | 10000000
Debt amount can range between 0 and the maximum amount of CAPEX
DSCR target | 1.7
Total Capex | 22796936.6
Cost of debt | 4.51%
First computation of the annual payment of debt | -1264409.6706
First Annual DSCR |  | -13.3968 | -1.5465 | 1.0995 | 2.4464 | 3.506 | 4.6603 | 5.916 | 7.28 | 8.7601 | 10.364 | 12.1003
The first 2 years we can't meet the DSCR requirements, so as said during lecture is assumed that Magnus made a deal with the bank to start repaing the debt after 2 year
New Annual Payment | -1516716.002
New DSCR |  |  |  | 0.91659 | 2.0394 | 2.9228 | 3.8851 | 4.9318 | 6.069 | 7.3028 | 8.6399 | 10.0874
In this step the debt to be contracted was first decided, then a DSCR target to be respected was set (usually the DSCR target must be greater than 1,5). Using the RATA (PMT in english) formula, the annual payment of debt was computed, but in this way there was a too low DSCR in the first two year.To solve this problem it was assumed that the company had an agreement with the bank to pay back the debt after 2 year, so when the factory is completed (to make this assumption realistic, a high cost of debt was chosen). So in this way a new annual payment of debt and new DSCRs were computed
3. Profitability with debt
Equity to use = CAPEX - DEBT | 12796936.6
Cost of equity of levered firm | 19.63%
WACC | 12.33%
Tax rate | 34%
NPV | 12245409.1858
Engineering, purchase etc year 2023 or 2024
Loan year 2023 and costs 2023 - ask prof
Clump sum in the beginning or divide debt
Overhead costs?, ask prof if assumtipons are ok -> Indirect costs?
Government subsidies
Joint venture funding
Contingency fund -> Risk analysis
Deprecation
DSCR > DSCR target
Residual value 30% of the initial one
To repay CAPEX we use only 49% of the net cashflow

## Cash Flow graph
Year | Net cash flow | Free Cash Flow | Net Cash Flow to repay the CAPEX | Cumulative Net cash flow | Cumulative free cash flow | Cumulative Net Cash Flow to repay the CAPEX
2024 | -16938999.692 | -18246823.692 | -16938999.692 | -13.67% | -16.66% | -32.52%
2025 | -3990739.732 | -5298563.732 | -1955462.4687 | -16.89% | -21.5% | -36.28%
2026 | 2837153.3931 | 1529329.3931 | 1390205.1626 | -14.6% | -20.1% | -33.61%
2027 | 6312639.0777 | 5004815.0777 | 3093193.1481 | -9.506% | -15.53% | -27.67%
2028 | 9046917.2357 | 7739093.2357 | 4432989.4455 | -2.206% | -8.465% | -19.16%
2029 | 12025553.5154 | 10717729.5154 | 5892521.2226 | 7.499% | 1.32% | -7.845%
2030 | 15265706.5196 | 13957882.5196 | 7480196.1946 | 19.82% | 14.06% | 6.518%
2031 | 18785619.0759 | 17477795.0759 | 9204953.3472 | 34.98% | 30.02% | 24.19%
2032 | 22604682.7888 | 21296858.7888 | 11076294.5665 | 53.22% | 49.46% | 45.46%
2033 | 26743506.2907 | 25435682.2907 | 13104318.0824 | 74.8% | 72.69% | 70.62%
2034 | 31223987.3985 | 29916163.3985 | 15299753.8253 | 100% | 100% | 100%
| 123916025.8715 | 109529961.8715 | 52079962.8341

## Revenues
2%
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
| 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034
Annual Total sales | 3668000 | 3844064 | 4028579.072 | 4221950.8675 | 4424604.5091 | 4636985.5255 | 4859560.8308 | 5092819.7506 | 5337275.0987 | 5593464.3034 | 5861950.59 | 6143324.2183
Annual sales on the aftermarket | 366800 | 384406.4 | 402857.9072 | 422195.0867 | 442460.4509 | 463698.5526 | 485956.0831 | 509281.9751 | 533727.5099 | 559346.4303 | 586195.059 | 614332.4218
Magnus share | 5% | 0% | 0% | 5% | 7% | 9% | 11% | 13% | 15% | 17% | 19% | 21%
Piece sold by Magnus to Manufacturers | 183400 | 0 | 0 | 211097.5434 | 309722.3156 | 417328.6973 | 534551.6914 | 662066.5676 | 800591.2648 | 950888.9316 | 1113770.6121 | 1290098.0858
Piece sold by Magnus in the aftermarket | 18340 | 0 | 0 | 21109.7543 | 30972.2316 | 41732.8697 | 53455.1691 | 66206.6568 | 80059.1265 | 95088.8932 | 111377.0612 | 129009.8086
Sales | 50435000000000 | 0 | 0 | 58051824.4275 | 85173636.8001 | 114765391.7569 | 147001715.1304 | 182068306.0851 | 220162597.8198 | 261494456.1839 | 306286918.3255 | 354776973.6056
EBITDA/Sales | 9% | 0% | 0% | 13.17% | 14% | 14% | 14% | 14% | 14% | 14% | 14% | 14%
EBITDA from sales | 4539150000000 | 0 | 0 | 7643490.2163 | 11924309.152 | 16067154.846 | 20580240.1183 | 25489562.8519 | 30822763.6948 | 36609223.8657 | 42880168.5656 | 49668776.3048
EBITDA to repay the CAPEX | 2224183500000 | 0 | 0 | 3745310.206 | 5842911.4845 | 7872905.8745 | 10084317.6579 | 12489885.7974 | 15103154.2104 | 17938519.6942 | 21011282.5971 | 24337700.3893
Revenues computation must start from 2024
Assumptions
|  | 3500000 | Units sold in the market at the end of 2023
Magnus has an initial market share of 5% and it increase of 2% every year
Magnus has an initial aftermarket share of 5% and it increase of 2% every year
The average price of the pieces sold by Magnus is 250€
We start to sell when the indian factory is completed (17/02/26)
Until project 3 is under realization, EBITDA/SALES=9%
After completion of project 3 (23/06/26), EBITDA/SALES=14%
The last row represent the earnings generated from selling the pieces on the market and aftermarket