Project charter – Project 3: Platform
Recognizing the shortcomings of its traditional functional structure overlaid on a macro-operation process, Magnus is preparing to change the complex network of organizational relationships hindering effective application development. Despite delivering specialized functions, this approach falls short of desired outcomes, particularly in monitoring and controlling development phases. The primary issue lies in the lack of clear accountability for development costs and quality metrics among application engineers and personnel. To address this, Magnus proposes a transformative shift to a matrix organization. Accordingly, the “Platform” project aims to establish a platform/program approach to product management, where specific customer applications are developed within a program of similar products.

Setting the change process into motion necessitates creating a compelling sense of urgency among both managers and employees. It is imperative that all stakeholders not only acknowledge the imperative for change but also grasp its fundamental role in propelling organizational growth. To do so, the shift to the matrix organization must consider both the opinions of employees and of industry expert regarding the current challenges and the necessity for change. Various teams of experts, described in the next paragraphs, must create a new corporate vision to show employees and customers the organization's desired future state.

Several obstacles can be encountered in this process, ranging from deficient processes to employee resistance and misaligned policies. In this phase, the guiding coalition and senior management play a pivotal role in recognizing and dismantling these barriers. A thorough review of processes, structures, policies, rewards, and communication channels is essential.

Once this is accomplished, management must create a set of medium-to-short goals that can be achieved and celebrated early in the process to maintain momentum. The last step of the project entails a transformation of organizational norms, values, processes, reward systems, and infrastructure elements, all harmonized to seamlessly align with the new company’s vision.

Moving on instead in the relationship of this project with the other initiatives, it can be seen that once the machinery needed in Project 1 has been secured and compensated for, a meeting is held among all stakeholders in Project 3 to initiate the planned activities. The activities have an expected start date on 01/15/25, all other tasks will follow a linear development, free from any specific time constraints. Only with the phase called "Removing barriers" will there be an iteration with Project 2. To identify inadequate processes, the senior guiding team will have to wait until the end of testing and then the beginning of the deployment of Project 2; this task is expected to begin on 06/04/26. A meeting is scheduled for the end of the project, which occurs between the project sponsor and the Italian CEO of Magnus. The purpose of the meeting is to showcase the progress achieved thus far.

Regarding the entities and resources involved, the first phase of the project will be completed by a team of business analysts who are industry experts and will analyse the future scenarios in which the company will have to navigate. Once this phase is completed, the "Building Guiding Coalition" phase will begin. In this phase all the key teams participating in the project will be created. In particular, the CEO of Magnus will choose the project sponsor, who in turn will designate the members of the Senior Guiding Team: the latter team will be empowered to make decisions on the new company’s vision, resource allocation, and removal of barriers hindering the success of the project. The Senior Guiding Team, together with the sponsor, will select the Field Guiding Team, which will have the role of communicating the vision and to guide the organization throughout the process. The last team that will participate in the project is the Change Team, who as true project managers will oversee bringing the tasks to completion within the agreed limits and simultaneously support the teams already mentioned in more complex decisions.

Moving on the expected outcome, it can be seen that completion of Project 3 will enable the new factory to have its own product development capability, which will have the direct effect of lowering production costs. Moreover, before the completion of project 3, products produced in India but designed in Italy will have an EBITDA profit margin (EBITDA / Sales) equals to 9%, instead after the completion of the project the profit margin for products completely developed in India is expected to be at 14%.

Lastly, regarding time and cost, the project will start on 01/15/25 and has an expected completion date on 06/23/26, with an expected cost of €337.752,28.

Attachment
Summary project charter
Project name	Project 3: Platform
Stakeholders	Magnus Italy, Magnus India
Objectives and Potential Constraints	The main objective of this project is to establish a platform/program approach to product management, where specific customer applications are developed within a program of similar products. The constraint is that it can start only after the completion of the manufacturing phase on Project 1, and the Test phase of project 2.
Relationships with other Initiaitives	We assumed that Projects 2 and 3 can commence concurrently. / ERP implementation phase completion of project 2 marks the beginning of the "Enable action by removing barriers" phase of Project 3.
Entities and Resources Involved	The project will be carried on by a business analyst and a Guiding Coalition. The Guiding Coalition will composed of a Sponsor, Senior Guiding Team, Field Guiding Team, Change Team. The Sponsor will be decided by the CEO and then each team will be chosen by the previous team in the order listed.
Expected Outcomes and Scheduled Dates	Project 3 will enable the new factory to have its own product development capability, which will have the direct effect of lowering production costs. EBITDA profit margin (EBITDA / Sales) will go from 9% to 14%. / The project will start on 01/15/25 and has an expected completion date on 06/23/26
Cost Estimate	Platform project has an expected cost of €337.752,28.