## Task_Table1
WBS | Name | Duration | Start_Date | Finish_Date | Predecessors | Successors | Resource_Names | Cost
1 | Project | 646,45 days | 15 January 2024 08:00 | 07 July 2026 11:36 |  |  |  | 25153237.88
1.1 | Project 1 | 546,95 days | 15 January 2024 08:00 | 17 February 2026 16:36 |  |  |  | 24606267.6
1.1.1 | ENGINEERING PHASE | 124,8 days | 15 January 2024 08:00 | 05 July 2024 15:24 |  |  |  | 1342464
1.1.1.1 | Detailed Engineering - Process | 124,8 days | 15 January 2024 08:00 | 05 July 2024 15:24 |  | 7 | Italian Project Engineer[200%];Italian Specialized Engineer;Crashing italian project engineering;Crashing italian specialized engineering | 918528
1.1.1.2 | Detailed Engineering - Layout | 115,2 days | 15 January 2024 08:00 | 24 June 2024 09:36 |  | 16;7 | Indian Project Engineer[200%];Indian Specialized Engineer[400%];Crashing indian specialized engineering;Crashing indian project engineering | 423936
1.1.2 | CIVIL WORKS REFURBISHMENT ERECTION PHASE | 173,5 days | 05 July 2024 15:24 | 06 March 2025 10:24 |  |  |  | 840
1.1.2.1 | Design Civil Works | 55 days | 05 July 2024 15:24 | 20 September 2024 15:24 | 5;4 | 8FS-25d | Owner | 0
1.1.2.2 | Permits and Authorizations | 30 days | 16 August 2024 15:24 | 27 September 2024 15:24 | 7FS-25d | 9FS-15d | Owner | 0
1.1.2.3 | Site Installation | 15 days | 06 September 2024 15:24 | 27 September 2024 15:24 | 8FS-15d | 10 | Owner | 0
1.1.2.4 | Excavations & Foundations | 30 days | 27 September 2024 15:24 | 08 November 2024 15:24 | 9 | 11FS-15d | Owner | 0
1.1.2.5 | Structural Improvement | 35 days | 18 October 2024 15:24 | 06 December 2024 15:24 | 10FS-15d | 12 | Owner | 0
1.1.2.6 | Industrial Flooring | 35 days | 06 December 2024 15:24 | 24 January 2025 15:24 | 11 | 82FF-50%;83FF-50%;84FF-45%;13FS-10d;85FF-45%;86FF-47%;87FF-50%;88FF-47%;89FF-50%;90FF-50%;91FF-50%;92FF-50%;93FF-50% | Owner | 0
1.1.2.7 | Finishes | 38 days | 10 January 2025 15:24 | 05 March 2025 15:24 | 12FS-10d | 14 | Owner | 0
1.1.2.8 | Civil work final meeting | 4 hrs | 05 March 2025 15:24 | 06 March 2025 10:24 | 13 | 284 | Owner;Indian Project Engineer;Italian Project Engineer | 840
1.1.3 | PURCHASE PROCESS (to repeat for each equipment type) | 14,88 days | 24 June 2024 09:36 | 15 July 2024 08:38 |  |  |  | 5885.6
1.1.3.1 | Request for proposals | 2,5 days | 24 June 2024 09:36 | 26 June 2024 14:36 | 5 | 17 | Purchasing agent[200%] | 2800
1.1.3.2 | Waiting period | 10 days | 26 June 2024 14:36 | 10 July 2024 14:36 | 16 | 18 | Supplier | 0
1.1.3.3 | Competitive proposal analysis | 2 days | 10 July 2024 14:36 | 12 July 2024 14:36 | 17 | 20;21;22;23 | Purchasing agent[200%] | 2240
1.1.3.4 | Orders | 0,38 days | 12 July 2024 14:36 | 15 July 2024 08:38 |  |  | Purchasing agent | 845.6
1.1.3.4.1 | CNC Machine (Double and Single spindle) order | 0,13 days | 12 July 2024 14:36 | 12 July 2024 15:38 | 18 | 31;35;24 | Purchasing agent | 72.8
1.1.3.4.2 | Drilling Machine order | 0,13 days | 12 July 2024 14:36 | 12 July 2024 15:36 | 18 | 39;25 | Purchasing agent | 70
1.1.3.4.3 | Conveyors order (Powered and Overhead) | 0,13 days | 12 July 2024 14:36 | 12 July 2024 15:36 | 18 | 43;47;26 | Purchasing agent | 70
1.1.3.4.4 | Washing station (Final and Intermidiate) order | 0,13 days | 12 July 2024 14:36 | 12 July 2024 15:36 | 18 | 51;55;27 | Purchasing agent | 70
1.1.3.4.5 | Assembly Station order | 0,13 days | 12 July 2024 15:38 | 12 July 2024 16:38 | 20 | 59;28 | Purchasing agent | 70
1.1.3.4.6 | Gantry Loader order | 0,13 days | 12 July 2024 15:36 | 12 July 2024 16:36 | 21 | 63 | Purchasing agent | 70
1.1.3.4.7 | Rotating Table | 0,13 days | 12 July 2024 15:36 | 12 July 2024 16:36 | 22 | 67 | Purchasing agent | 70
1.1.3.4.8 | Lift/Lower Components | 0,13 days | 12 July 2024 15:36 | 12 July 2024 16:36 | 23 | 71 | Purchasing agent | 70
1.1.3.4.9 | Manipulator | 0,13 days | 12 July 2024 16:38 | 15 July 2024 08:38 | 24 | 75 | Purchasing agent | 70
1.1.4 | EQUIPMENT MANUFACTURING PHASE (values for each unit of equipment) | 132,38 days | 12 July 2024 15:36 | 15 January 2025 09:38 |  |  |  | 18680878
1.1.4.1 | Single Spindle machine | 111,13 days | 12 July 2024 15:38 | 16 December 2024 16:38 |  |  |  | 1020070
1.1.4.1.1 | Single Spindle Machine | 110 days | 12 July 2024 15:38 | 13 December 2024 15:38 | 20 | 32 | Supplier | 1020000
1.1.4.1.2 | Technical requiremets check | 1 day | 13 December 2024 15:38 | 16 December 2024 15:38 | 31 | 33 | Supplier | 0
1.1.4.1.3 | Payment | 1 hr | 16 December 2024 15:38 | 16 December 2024 16:38 | 32 | 82;79;80 | Purchasing agent | 70
1.1.4.2 | Double Spindle Machine | 111,13 days | 12 July 2024 15:38 | 16 December 2024 16:38 |  |  |  | 11000070
1.1.4.2.1 | Double Spindle machine | 110 days | 12 July 2024 15:38 | 13 December 2024 15:38 | 20 | 36 | Supplier | 11000000
1.1.4.2.2 | Technical requiremets check | 1 day | 13 December 2024 15:38 | 16 December 2024 15:38 | 35 | 37 | Supplier | 0
1.1.4.2.3 | Payment | 1 hr | 16 December 2024 15:38 | 16 December 2024 16:38 | 36 | 83;79;80 | Purchasing agent | 70
1.1.4.3 | Drilling machine | 67,13 days | 12 July 2024 15:36 | 15 October 2024 16:36 |  |  |  | 270070
1.1.4.3.1 | Drilling machine | 66 days | 12 July 2024 15:36 | 14 October 2024 15:36 | 21 | 40 | Supplier | 270000
1.1.4.3.2 | Technical requiremets check | 1 day | 14 October 2024 15:36 | 15 October 2024 15:36 | 39 | 41 | Supplier | 0
1.1.4.3.3 | Payment | 1 hr | 15 October 2024 15:36 | 15 October 2024 16:36 | 40 | 84;79;80 | Purchasing agent | 70
1.1.4.4 | Powered Conveyors | 131,13 days | 12 July 2024 15:36 | 13 January 2025 16:36 |  |  |  | 250070
1.1.4.4.1 | Powered conveyors | 130 days | 12 July 2024 15:36 | 10 January 2025 15:36 | 22 | 44 | Supplier | 250000
1.1.4.4.2 | Technical requiremets check | 1 day | 10 January 2025 15:36 | 13 January 2025 15:36 | 43 | 45 | Supplier | 0
1.1.4.4.3 | Payment | 1 hr | 13 January 2025 15:36 | 13 January 2025 16:36 | 44 | 85;79;80 | Purchasing agent | 70
1.1.4.5 | Overhead Conveyors | 131,13 days | 12 July 2024 15:36 | 13 January 2025 16:36 |  |  |  | 70270
1.1.4.5.1 | Overhead Conveyors | 130 days | 12 July 2024 15:36 | 10 January 2025 15:36 | 22 | 48 | Supplier | 70200
1.1.4.5.2 | Technical requiremets check | 1 day | 10 January 2025 15:36 | 13 January 2025 15:36 | 47 | 49 | Supplier | 0
1.1.4.5.3 | Payment | 1 hr | 13 January 2025 15:36 | 13 January 2025 16:36 | 48 | 86;79;80 | Purchasing agent | 70
1.1.4.6 | Intermidiate Washing stations | 71,13 days | 12 July 2024 15:36 | 21 October 2024 16:36 |  |  |  | 530070
1.1.4.6.1 | Intermidiate Washing stations | 70 days | 12 July 2024 15:36 | 18 October 2024 15:36 | 23 | 52 | Supplier | 530000
1.1.4.6.2 | Technical requiremets check | 1 day | 18 October 2024 15:36 | 21 October 2024 15:36 | 51 | 53 | Supplier | 0
1.1.4.6.3 | Payment | 1 hr | 21 October 2024 15:36 | 21 October 2024 16:36 | 52 | 91;79;80 | Purchasing agent | 70
1.1.4.7 | Final Washing station | 71,13 days | 12 July 2024 15:36 | 21 October 2024 16:36 |  |  |  | 970070
1.1.4.7.1 | Final Washing station | 70 days | 12 July 2024 15:36 | 18 October 2024 15:36 | 23 | 56 | Supplier | 970000
1.1.4.7.2 | Technical requiremets check | 1 day | 18 October 2024 15:36 | 21 October 2024 15:36 | 55 | 57 | Supplier | 0
1.1.4.7.3 | Payment | 1 hr | 21 October 2024 15:36 | 21 October 2024 16:36 | 56 | 92;79;80 | Purchasing agent | 70
1.1.4.8 | Assembly station | 101,13 days | 12 July 2024 16:38 | 03 December 2024 08:38 |  |  |  | 2200070
1.1.4.8.1 | Assembly station | 100 days | 12 July 2024 16:38 | 29 November 2024 16:38 | 24 | 60 | Supplier | 2200000
1.1.4.8.2 | Technical requiremets check | 1 day | 29 November 2024 16:38 | 02 December 2024 16:38 | 59 | 61 | Supplier | 0
1.1.4.8.3 | Payment | 1 hr | 02 December 2024 16:38 | 03 December 2024 08:38 | 60 | 93;79;80 | Purchasing agent | 70
1.1.4.9 | Gantry loaders | 96,13 days | 12 July 2024 16:36 | 26 November 2024 08:36 |  |  |  | 2200070
1.1.4.9.1 | Gantry loaders | 95 days | 12 July 2024 16:36 | 22 November 2024 16:36 | 25 | 64 | Supplier | 2200000
1.1.4.9.2 | Technical requiremets check | 1 day | 22 November 2024 16:36 | 25 November 2024 16:36 | 63 | 65 | Supplier | 0
1.1.4.9.3 | Payment | 1 hr | 25 November 2024 16:36 | 26 November 2024 08:36 | 64 | 88;79;80 | Purchasing agent | 70
1.1.4.10 | Rotating Table | 131,13 days | 12 July 2024 16:36 | 14 January 2025 08:36 |  |  |  | 112070
1.1.4.10.1 | Rotating Table | 130 days | 12 July 2024 16:36 | 10 January 2025 16:36 | 26 | 68 | Supplier | 112000
1.1.4.10.2 | Technical requiremets check | 1 day | 10 January 2025 16:36 | 13 January 2025 16:36 | 67 | 69 | Supplier | 0
1.1.4.10.3 | Payment | 1 hr | 13 January 2025 16:36 | 14 January 2025 08:36 | 68 | 89;79;80 | Purchasing agent | 70
1.1.4.11 | Lift/Lower Components | 131,13 days | 12 July 2024 16:36 | 14 January 2025 08:36 |  |  |  | 32470
1.1.4.11.1 | Lift/Lower Components | 130 days | 12 July 2024 16:36 | 10 January 2025 16:36 | 27 | 72 | Supplier | 32400
1.1.4.11.2 | Technical requiremets check | 1 day | 10 January 2025 16:36 | 13 January 2025 16:36 | 71 | 73 | Supplier | 0
1.1.4.11.3 | Payment | 1 hr | 13 January 2025 16:36 | 14 January 2025 08:36 | 72 | 90;79;80 | Purchasing agent | 70
1.1.4.12 | Manipulator | 131,13 days | 15 July 2024 08:38 | 14 January 2025 09:38 |  |  |  | 22070
1.1.4.12.1 | Manipulator | 130 days | 15 July 2024 08:38 | 13 January 2025 08:38 | 28 | 76 | Supplier | 22000
1.1.4.12.2 | Technical requiremets check | 1 day | 13 January 2025 08:38 | 14 January 2025 08:38 | 75 | 77 | Supplier | 0
1.1.4.12.3 | Payment | 1 hr | 14 January 2025 08:38 | 14 January 2025 09:38 | 76 | 87;79;80 | Purchasing agent | 70
1.1.4.13 | Meeting to start project 2 & 3 | 1 day | 14 January 2025 09:38 | 15 January 2025 09:38 |  |  |  | 3438
1.1.4.13.1 | Meeting to start project 2 | 4 hrs | 14 January 2025 09:38 | 14 January 2025 14:38 | 33;37;41;45;49;53;57;61;65;69;73;77 | 187FS+1d;80 | CEO IN;CEO IT;Purchasing agent;Project Director | 1280
1.1.4.13.2 | Meeting to start project 3 | 4 hrs | 14 January 2025 14:38 | 15 January 2025 09:38 | 33;37;41;45;49;53;57;61;65;69;73;77;79 | 232 | CEO IN;CEO IT;Purchasing agent;Senior guiding team | 2158
1.1.5 | TRANSPORTATION PHASE (from the contractor to the owner's construction site) | 124,26 days | 15 October 2024 16:36 | 08 April 2025 09:38 |  |  |  | 143000
1.1.5.1 | Single Spindle Machine | 60 days | 16 December 2024 16:38 | 10 March 2025 16:38 | 12FF-50%;33 | 97;101;137 | Transportation Company | 10000
1.1.5.2 | Double Spindle Machine | 60 days | 16 December 2024 16:38 | 10 March 2025 16:38 | 12FF-50%;37 | 111;115;120;124;129;133;152;156;161;165;169 | Transportation Company | 55000
1.1.5.3 | Drilling Machine | 60 days | 15 October 2024 16:36 | 07 January 2025 16:36 | 12FF-45%;41 | 106 | Transportation Company | 5000
1.1.5.4 | Powered Conveyors | 15 days | 13 January 2025 16:36 | 03 February 2025 16:36 | 12FF-45%;45 | 183 | Transportation Company | 7500
1.1.5.5 | Overhead Conveyors | 15 days | 13 January 2025 16:36 | 03 February 2025 16:36 | 12FF-47%;49 | 183 | Transportation Company | 1500
1.1.5.6 | Manipulator | 60 days | 14 January 2025 09:38 | 08 April 2025 09:38 | 12FF-50%;77 | 183 | Transportation Company | 5000
1.1.5.7 | Gantry Loader | 60 days | 26 November 2024 08:36 | 18 February 2025 08:36 | 12FF-47%;65 | 183 | Transportation Company | 35000
1.1.5.8 | Rotating table | 45 days | 14 January 2025 08:36 | 18 March 2025 08:36 | 12FF-50%;69 | 183 | Transportation Company | 3500
1.1.5.9 | Lift/Lower Components | 60 days | 14 January 2025 08:36 | 08 April 2025 08:36 | 12FF-50%;73 | 183 | Transportation Company | 5000
1.1.5.10 | Intermidiate washing station | 45 days | 30 October 2024 10:24 | 01 January 2025 10:24 | 12FF-50%;53 | 142 | Transportation Company | 7000
1.1.5.11 | Final washing station | 45 days | 30 October 2024 10:24 | 01 January 2025 10:24 | 12FF-50%;57 | 174 | Transportation Company | 7000
1.1.5.12 | Assembly station | 15 days | 11 December 2024 10:24 | 01 January 2025 10:24 | 12FF-50%;61 | 147;179 | Transportation Company | 1500
1.1.6 | ON SITE ERECTION PHASE | 274,65 days | 01 January 2025 10:24 | 20 January 2026 16:36 |  |  |  | 4359600
1.1.6.1 | OP.10 | 90 days | 10 March 2025 16:38 | 14 July 2025 16:38 |  |  |  | 370800
1.1.6.1.1 | Single-spindle cnc machine 1 | 45 days | 10 March 2025 16:38 | 12 May 2025 16:38 |  |  |  | 185400
1.1.6.1.1.1 | Installation | 45 days | 10 March 2025 16:38 | 12 May 2025 16:38 | 147;82 | 98SS;101 | Team of Indian workers (4 workers each)[300%] | 70200
1.1.6.1.1.2 | Electrical&IT Connections | 5 days | 10 March 2025 16:38 | 17 March 2025 16:38 | 97SS;149 | 99 | Team of Italian workers (4 workers each)[300%] | 38400
1.1.6.1.1.3 | Final Assembly | 10 days | 17 March 2025 16:38 | 31 March 2025 16:38 | 98 | 102 | Team of Italian workers (4 workers each)[300%] | 76800
1.1.6.1.2 | Single-spindle cnc machine 2 | 45 days | 12 May 2025 16:38 | 14 July 2025 16:38 |  |  |  | 185400
1.1.6.1.2.1 | Installation | 45 days | 12 May 2025 16:38 | 14 July 2025 16:38 | 97;82 | 102SS;183;129 | Team of Indian workers (4 workers each)[300%] | 70200
1.1.6.1.2.2 | Electrical&IT Connections | 5 days | 12 May 2025 16:38 | 19 May 2025 16:38 | 101SS;99 | 103 | Team of Italian workers (4 workers each)[300%] | 38400
1.1.6.1.2.3 | Final Assembly | 10 days | 19 May 2025 16:38 | 02 June 2025 16:38 | 102 | 130 | Team of Italian workers (4 workers each)[300%] | 76800
1.1.6.2 | OP.20 | 90 days | 07 January 2025 16:36 | 13 May 2025 16:36 |  |  |  | 370800
1.1.6.2.1 | Drilling machine | 90 days | 07 January 2025 16:36 | 13 May 2025 16:36 |  |  |  | 370800
1.1.6.2.1.1 | Installation | 90 days | 07 January 2025 16:36 | 13 May 2025 16:36 | 84 | 107SS;183;111 | Team of Indian workers (4 workers each)[300%] | 140400
1.1.6.2.1.2 | Electrical&IT Connections | 10 days | 07 January 2025 16:36 | 21 January 2025 16:36 | 106SS | 108 | Team of Italian workers (4 workers each)[300%] | 76800
1.1.6.2.1.3 | Final Assembly | 20 days | 21 January 2025 16:36 | 18 February 2025 16:36 | 107 | 112 | Team of Italian workers (4 workers each)[300%] | 153600
1.1.6.3 | OP.30 | 45 days | 13 May 2025 16:36 | 15 July 2025 16:36 |  |  |  | 441000
1.1.6.3.1 | Double-spindle CNC machine 1 | 22,5 days | 13 May 2025 16:36 | 13 June 2025 11:36 |  |  |  | 220500
1.1.6.3.1.1 | Installation | 22,5 days | 13 May 2025 16:36 | 13 June 2025 11:36 | 106;83 | 115;112SS | Crashing Team Indian workers[300%];Team of Indian workers (4 workers each)[300%] | 105300
1.1.6.3.1.2 | Electrical&IT Connections | 5 days | 13 May 2025 16:36 | 20 May 2025 16:36 | 111SS;108 | 113 | Team of Italian workers (4 workers each)[300%] | 38400
1.1.6.3.1.3 | Final Assembly | 10 days | 20 May 2025 16:36 | 03 June 2025 16:36 | 112 | 116 | Team of Italian workers (4 workers each)[300%] | 76800
1.1.6.3.2 | Double-spindle CNC machine 2 | 22,5 days | 13 June 2025 11:36 | 15 July 2025 16:36 |  |  |  | 220500
1.1.6.3.2.1 | Installation | 22,5 days | 13 June 2025 11:36 | 15 July 2025 16:36 | 111;83 | 116SS;183;152 | Crashing Team Indian workers[300%];Team of Indian workers (4 workers each)[300%] | 105300
1.1.6.3.2.2 | Electrical&IT Connections | 5 days | 13 June 2025 11:36 | 20 June 2025 11:36 | 115SS;113 | 117 | Team of Italian workers (4 workers each)[300%] | 38400
1.1.6.3.2.3 | Final Assembly | 10 days | 20 June 2025 11:36 | 04 July 2025 11:36 | 116 | 153 | Team of Italian workers (4 workers each)[300%] | 76800
1.1.6.4 | OP.40 | 90 days | 07 May 2025 10:24 | 10 September 2025 10:24 |  |  |  | 370800
1.1.6.4.1 | Double-spindle CNC machine 3 | 45 days | 07 May 2025 10:24 | 09 July 2025 10:24 |  |  |  | 185400
1.1.6.4.1.1 | Installation | 45 days | 07 May 2025 10:24 | 09 July 2025 10:24 | 142;83 | 121SS;124 | Team of Indian workers (4 workers each)[300%] | 70200
1.1.6.4.1.2 | Electrical&IT Connections | 5 days | 07 May 2025 10:24 | 14 May 2025 10:24 | 120SS;144 | 122 | Team of Italian workers (4 workers each)[300%] | 38400
1.1.6.4.1.3 | Final Assembly | 10 days | 14 May 2025 10:24 | 28 May 2025 10:24 | 121 | 125 | Team of Italian workers (4 workers each)[300%] | 76800
1.1.6.4.2 | Double-spindle CNC machine 4 | 45 days | 09 July 2025 10:24 | 10 September 2025 10:24 |  |  |  | 185400
1.1.6.4.2.1 | Installation | 45 days | 09 July 2025 10:24 | 10 September 2025 10:24 | 120;83 | 125SS;183;161 | Team of Indian workers (4 workers each)[300%] | 70200
1.1.6.4.2.2 | Electrical&IT Connections | 5 days | 09 July 2025 10:24 | 16 July 2025 10:24 | 124SS;122 | 126 | Team of Italian workers (4 workers each)[300%] | 38400
1.1.6.4.2.3 | Final Assembly | 10 days | 16 July 2025 10:24 | 30 July 2025 10:24 | 125 | 162 | Team of Italian workers (4 workers each)[300%] | 76800
1.1.6.5 | OP.50 | 90 days | 14 July 2025 16:38 | 17 November 2025 16:38 |  |  |  | 370800
1.1.6.5.1 | Double-spindle CNC machine 5 | 30 days | 14 July 2025 16:38 | 25 August 2025 16:38 |  |  |  | 123600
1.1.6.5.1.1 | Installation | 30 days | 14 July 2025 16:38 | 25 August 2025 16:38 | 101;83 | 130SS;133 | Team of Indian workers (4 workers each)[300%] | 46800
1.1.6.5.1.2 | Electrical&IT Connections | 3,33 days | 14 July 2025 16:38 | 18 July 2025 10:17 | 129SS;103 | 131 | Team of Italian workers (4 workers each)[300%] | 25574.4
1.1.6.5.1.3 | Final Assembly | 6,67 days | 18 July 2025 10:17 | 28 July 2025 16:38 | 130 | 134 | Team of Italian workers (4 workers each)[300%] | 51225.6
1.1.6.5.2 | Double-spindle CNC machine 6 | 30 days | 25 August 2025 16:38 | 06 October 2025 16:38 |  |  |  | 123600
1.1.6.5.2.1 | Installation | 30 days | 25 August 2025 16:38 | 06 October 2025 16:38 | 129;83 | 134SS;137 | Team of Indian workers (4 workers each)[300%] | 46800
1.1.6.5.2.2 | Electrical&IT Connections | 3,33 days | 25 August 2025 16:38 | 29 August 2025 10:17 | 133SS;131 | 135 | Team of Italian workers (4 workers each)[300%] | 25574.4
1.1.6.5.2.3 | Final Assembly | 6,67 days | 29 August 2025 10:17 | 08 September 2025 16:38 | 134 | 138 | Team of Italian workers (4 workers each)[300%] | 51225.6
1.1.6.5.3 | Single-spindle cnc machine 3 | 30 days | 06 October 2025 16:38 | 17 November 2025 16:38 |  |  |  | 123600
1.1.6.5.3.1 | Installation | 30 days | 06 October 2025 16:38 | 17 November 2025 16:38 | 133;82 | 138SS;183;174 | Team of Indian workers (4 workers each)[300%] | 46800
1.1.6.5.3.2 | Electrical&IT Connections | 3,33 days | 06 October 2025 16:38 | 10 October 2025 10:17 | 137SS;135 | 139 | Team of Italian workers (4 workers each)[300%] | 25574.4
1.1.6.5.3.3 | Final Assembly | 6,67 days | 10 October 2025 10:17 | 20 October 2025 16:38 | 138 | 175 | Team of Italian workers (4 workers each)[300%] | 51225.6
1.1.6.6 | OP.60 | 90 days | 01 January 2025 10:24 | 07 May 2025 10:24 |  |  |  | 370800
1.1.6.6.1 | Intermediate washing station | 90 days | 01 January 2025 10:24 | 07 May 2025 10:24 |  |  |  | 370800
1.1.6.6.1.1 | Installation | 90 days | 01 January 2025 10:24 | 07 May 2025 10:24 | 91 | 143SS;183;120 | Team of Indian workers (4 workers each)[300%] | 140400
1.1.6.6.1.2 | Electrical&IT Connections | 10 days | 01 January 2025 10:24 | 15 January 2025 10:24 | 142SS | 144 | Team of Italian workers (4 workers each)[300%] | 76800
1.1.6.6.1.3 | Final Assembly | 20 days | 15 January 2025 10:24 | 12 February 2025 10:24 | 143 | 121 | Team of Italian workers (4 workers each)[300%] | 153600
1.1.6.7 | OP.70 | 45 days | 01 January 2025 10:24 | 05 March 2025 10:24 |  |  |  | 441000
1.1.6.7.1 | Valve guides assembly station | 45 days | 01 January 2025 10:24 | 05 March 2025 10:24 |  |  |  | 441000
1.1.6.7.1.1 | Installation | 45 days | 01 January 2025 10:24 | 05 March 2025 10:24 | 93 | 148SS;183;97 | Crashing Team Indian workers[300%];Team of Indian workers (4 workers each)[300%] | 210600
1.1.6.7.1.2 | Electrical&IT Connections | 10 days | 01 January 2025 10:24 | 15 January 2025 10:24 | 147SS | 149 | Team of Italian workers (4 workers each)[300%] | 76800
1.1.6.7.1.3 | Final Assembly | 20 days | 15 January 2025 10:24 | 12 February 2025 10:24 | 148 | 98 | Team of Italian workers (4 workers each)[300%] | 153600
1.1.6.8 | OP.80 | 45 days | 15 July 2025 16:36 | 16 September 2025 16:36 |  |  |  | 441000
1.1.6.8.1 | Double-spindle CNC machine 7 | 22,5 days | 15 July 2025 16:36 | 15 August 2025 11:36 |  |  |  | 220500
1.1.6.8.1.1 | Installation | 22,5 days | 15 July 2025 16:36 | 15 August 2025 11:36 | 115;83 | 153SS;156 | Crashing Team Indian workers[300%];Team of Indian workers (4 workers each)[300%] | 105300
1.1.6.8.1.2 | Electrical&IT Connections | 5 days | 15 July 2025 16:36 | 22 July 2025 16:36 | 152SS;117 | 154 | Team of Italian workers (4 workers each)[300%] | 38400
1.1.6.8.1.3 | Final Assembly | 10 days | 22 July 2025 16:36 | 05 August 2025 16:36 | 153 | 157 | Team of Italian workers (4 workers each)[300%] | 76800
1.1.6.8.2 | Double-spindle CNC machine 8 | 22,5 days | 15 August 2025 11:36 | 16 September 2025 16:36 |  |  |  | 220500
1.1.6.8.2.1 | Installation | 22,5 days | 15 August 2025 11:36 | 16 September 2025 16:36 | 152;83 | 157SS;183;179 | Crashing Team Indian workers[300%];Team of Indian workers (4 workers each)[300%] | 105300
1.1.6.8.2.2 | Electrical&IT Connections | 5 days | 15 August 2025 11:36 | 22 August 2025 11:36 | 156SS;154 | 158 | Team of Italian workers (4 workers each)[300%] | 38400
1.1.6.8.2.3 | Final Assembly | 10 days | 22 August 2025 11:36 | 05 September 2025 11:36 | 157 | 180 | Team of Italian workers (4 workers each)[300%] | 76800
1.1.6.9 | OP.90 | 90 days | 10 September 2025 10:24 | 14 January 2026 10:24 |  |  |  | 370800
1.1.6.9.1 | Double-Spindle CNC machine 9 | 30 days | 10 September 2025 10:24 | 22 October 2025 10:24 |  |  |  | 123600
1.1.6.9.1.1 | Installation | 30 days | 10 September 2025 10:24 | 22 October 2025 10:24 | 124;83 | 162SS;165 | Team of Indian workers (4 workers each)[300%] | 46800
1.1.6.9.1.2 | Electrical&IT Connections | 3,33 days | 10 September 2025 10:24 | 15 September 2025 14:02 | 161SS;126 | 163 | Team of Italian workers (4 workers each)[300%] | 25574.4
1.1.6.9.1.3 | Final Assembly | 6,67 days | 15 September 2025 14:02 | 24 September 2025 10:24 | 162 | 166 | Team of Italian workers (4 workers each)[300%] | 51225.6
1.1.6.9.2 | Double-Spindle CNC machine 10 | 30 days | 22 October 2025 10:24 | 03 December 2025 10:24 |  |  |  | 123600
1.1.6.9.2.1 | Installation | 30 days | 22 October 2025 10:24 | 03 December 2025 10:24 | 161;83 | 166SS;169 | Team of Indian workers (4 workers each)[300%] | 46800
1.1.6.9.2.2 | Electrical&IT Connections | 3,33 days | 22 October 2025 10:24 | 27 October 2025 14:02 | 165SS;163 | 167 | Team of Italian workers (4 workers each)[300%] | 25574.4
1.1.6.9.2.3 | Final Assembly | 6,67 days | 27 October 2025 14:02 | 05 November 2025 10:24 | 166 | 170 | Team of Italian workers (4 workers each)[300%] | 51225.6
1.1.6.9.3 | Double-Spindle CNC machine 11 | 30 days | 03 December 2025 10:24 | 14 January 2026 10:24 |  |  |  | 123600
1.1.6.9.3.1 | Installation | 30 days | 03 December 2025 10:24 | 14 January 2026 10:24 | 165;83 | 170SS;183 | Team of Indian workers (4 workers each)[300%] | 46800
1.1.6.9.3.2 | Electrical&IT Connections | 3,33 days | 03 December 2025 10:24 | 08 December 2025 14:02 | 169SS;167 | 171 | Team of Italian workers (4 workers each)[300%] | 25574.4
1.1.6.9.3.3 | Final Assembly | 6,67 days | 08 December 2025 14:02 | 17 December 2025 10:24 | 170 | 183 | Team of Italian workers (4 workers each)[300%] | 51225.6
1.1.6.10 | OP.100 | 45 days | 17 November 2025 16:38 | 19 January 2026 16:38 |  |  |  | 441000
1.1.6.10.1 | Final washing station | 45 days | 17 November 2025 16:38 | 19 January 2026 16:38 |  |  |  | 441000
1.1.6.10.1.1 | Installation | 45 days | 17 November 2025 16:38 | 19 January 2026 16:38 | 137;92 | 175SS;183 | Team of Indian workers (4 workers each)[300%];Crashing Team Indian workers[300%] | 210600
1.1.6.10.1.2 | Electrical&IT Connections | 10 days | 17 November 2025 16:38 | 01 December 2025 16:38 | 174SS;139 | 176 | Team of Italian workers (4 workers each)[300%] | 76800
1.1.6.10.1.3 | Final Assembly | 20 days | 01 December 2025 16:38 | 29 December 2025 16:38 | 175 | 183 | Team of Italian workers (4 workers each)[300%] | 153600
1.1.6.11 | OP.110 | 90 days | 16 September 2025 16:36 | 20 January 2026 16:36 |  |  |  | 370800
1.1.6.11.1 | Final assembly station | 90 days | 16 September 2025 16:36 | 20 January 2026 16:36 |  |  |  | 370800
1.1.6.11.1.1 | Installation | 90 days | 16 September 2025 16:36 | 20 January 2026 16:36 | 156;93 | 180SS;183 | Team of Indian workers (4 workers each)[300%] | 140400
1.1.6.11.1.2 | Electrical&IT Connections | 10 days | 16 September 2025 16:36 | 30 September 2025 16:36 | 179SS;158 | 181 | Team of Italian workers (4 workers each)[300%] | 76800
1.1.6.11.1.3 | Final Assembly | 20 days | 30 September 2025 16:36 | 28 October 2025 16:36 | 180 | 183 | Team of Italian workers (4 workers each)[300%] | 153600
1.1.7 | FINAL LINE TESTING | 20 days | 20 January 2026 16:36 | 17 February 2026 16:36 |  |  |  | 73600
1.1.7.1 | Testing | 20 days | 20 January 2026 16:36 | 17 February 2026 16:36 | 179;174;169;156;147;142;137;124;115;106;101;171;176;181;85;86;87;88;89;90 | 213;284 | Italian Project Engineer[200%];Team of Italian workers (4 workers each) | 73600
1.2 | Project2 | 382,75 days | 15 January 2025 14:38 | 06 July 2026 11:36 |  |  |  | 207682
1.2.1 | ERP Implementation | 381,75 days | 15 January 2025 14:38 | 03 July 2026 11:36 |  |  |  | 205682
1.2.1.1 | Prepare | 40 days | 15 January 2025 14:38 | 12 March 2025 14:38 |  |  |  | 47680
1.2.1.1.1 | Plan the meeting and revise requirements | 8 days | 15 January 2025 14:38 | 27 January 2025 14:38 | 79FS+1d | 189 | ERP Expert IT;Project Director | 6464
1.2.1.1.2 | Develop projet plan | 8 days | 27 January 2025 14:38 | 06 February 2025 14:38 |  |  |  | 6464
1.2.1.1.2.1 | Develop Project Charter | 2 days | 27 January 2025 14:38 | 29 January 2025 14:38 | 187 | 190 | Project Director;ERP Expert IT | 1616
1.2.1.1.2.2 | Define project and quality management processes | 2 days | 29 January 2025 14:38 | 31 January 2025 14:38 | 189 | 191 | Project Director;ERP Expert IT | 1616
1.2.1.1.2.3 | Create Master Plan | 2 days | 31 January 2025 14:38 | 04 February 2025 14:38 | 190 | 192 | Project Director;ERP Expert IT | 1616
1.2.1.1.2.4 | Craft detailed work plan | 2 days | 04 February 2025 14:38 | 06 February 2025 14:38 | 191 | 193 | Project Director;ERP Expert IT | 1616
1.2.1.1.3 | Validate and prioritize requirements | 8 days | 06 February 2025 14:38 | 18 February 2025 14:38 | 192 | 195 | ERP Expert IT;Project Director | 6464
1.2.1.1.4 | Establish governance and communicating strategy | 8 days | 18 February 2025 14:38 | 28 February 2025 14:38 |  |  |  | 16000
1.2.1.1.4.1 | Establish organizational structure | 3 days | 18 February 2025 14:38 | 21 February 2025 14:38 | 193 | 196 | CEO IN;CEO IT;Project Director | 6000
1.2.1.1.4.2 | Devise project tool strategy | 3 days | 21 February 2025 14:38 | 26 February 2025 14:38 | 195 | 197 | CEO IN;CEO IT;Project Director | 6000
1.2.1.1.4.3 | Assign resources to tasks | 2 days | 26 February 2025 14:38 | 28 February 2025 14:38 | 196 | 198 | CEO IN;CEO IT;Project Director | 4000
1.2.1.1.5 | Hire resources | 8 days | 28 February 2025 14:38 | 12 March 2025 14:38 | 197 | 200 | CEO IN;CEO IT | 12288
1.2.1.2 | Explore | 60 days | 12 March 2025 14:38 | 04 June 2025 14:38 |  |  |  | 48080
1.2.1.2.1 | Perform AS IS analysis | 10 days | 12 March 2025 14:38 | 26 March 2025 14:38 | 198 | 201 | Business Analyst IT | 3040
1.2.1.2.2 | Perform FIT GAP analysis | 10 days | 26 March 2025 14:38 | 09 April 2025 14:38 | 200 | 202 | Business Analyst IT;ERP Expert IT;Functional Manager IN;Functional Manager IT;Functional Professional IN;Functional Professional IT | 16040
1.2.1.2.3 | Perform TO BE analysis | 10 days | 09 April 2025 14:38 | 23 April 2025 14:38 | 201 | 203 | Business Analyst IT | 3040
1.2.1.2.4 | Develop functional specification and realization plan | 10 days | 23 April 2025 14:38 | 07 May 2025 14:38 | 202 | 204 | Business Analyst IT;ERP Expert IT | 6480
1.2.1.2.5 | Develop security, privacy and controls approach | 10 days | 07 May 2025 14:38 | 21 May 2025 14:38 | 203 | 205 | ERP Expert IT | 3440
1.2.1.2.6 | Develop Business Process Blueprints | 10 days | 21 May 2025 14:38 | 04 June 2025 14:38 | 204 | 207 | Business Analyst IT;ERP Expert IT;Functional Manager IN;Functional Manager IT;Functional Professional IN;Functional Professional IT | 16040
1.2.1.3 | Build | 100 days | 04 June 2025 14:38 | 22 October 2025 14:38 |  |  |  | 56880
1.2.1.3.1 | Develop technical specifications | 20 days | 04 June 2025 14:38 | 02 July 2025 14:38 | 205 | 208 | ERP Expert IT;ERP Professional IN;Functional Professional IN;Functional Professional IT | 16320
1.2.1.3.2 | Develop configuration and code | 20 days | 02 July 2025 14:38 | 30 July 2025 14:38 | 207 | 209 | ERP Expert IT;ERP Professional IN | 8080
1.2.1.3.3 | Perform unit test | 20 days | 30 July 2025 14:38 | 27 August 2025 14:38 | 208 | 210 | ERP Expert IT;ERP Professional IN | 8080
1.2.1.3.4 | Develop learning documentation | 20 days | 27 August 2025 14:38 | 24 September 2025 14:38 | 209 | 211 | ERP Expert IT;ERP Professional IN | 8080
1.2.1.3.5 | Develop Go/No Go criteria and deployment plan | 20 days | 24 September 2025 14:38 | 22 October 2025 14:38 | 210 | 213 | ERP Expert IT;ERP Professional IN;Functional Professional IN;Functional Professional IT | 16320
1.2.1.4 | Test | 33 days | 17 February 2026 16:36 | 03 April 2026 16:36 |  |  |  | 19224
1.2.1.4.1 | Conduct integration test | 6 days | 17 February 2026 16:36 | 25 February 2026 16:36 | 211;183 | 214 | ERP Professional IN;ERP Expert IT | 2424
1.2.1.4.2 | Conduct mock data conversion | 6 days | 25 February 2026 16:36 | 05 March 2026 16:36 | 213 | 215 | ERP Professional IN;ERP Expert IT | 2424
1.2.1.4.3 | Develop a transition plan | 3 days | 05 March 2026 16:36 | 10 March 2026 16:36 | 214 | 216 | Business Analyst IT;ERP Expert IT;ERP Professional IN;Functional Manager IN;Functional Manager IT;Functional Professional IN;Functional Professional IT | 4992
1.2.1.4.4 | Prepare for user acceptance test | 12 days | 10 March 2026 16:36 | 26 March 2026 16:36 | 215 | 217 | Business Analyst IT | 3648
1.2.1.4.5 | Conduct acceptance test | 6 days | 26 March 2026 16:36 | 03 April 2026 16:36 | 216 | 219 | Functional Professional IT;Functional Manager IN;Functional Manager IT;Functional Professional IN | 5736
1.2.1.5 | Deploy | 24,5 days | 03 April 2026 16:36 | 08 May 2026 11:36 |  |  |  | 11178
1.2.1.5.1 | Meeting to start project 3 | 4 hrs | 03 April 2026 16:36 | 06 April 2026 11:36 | 217 | 220;257 | Senior guiding team;Sponsor;CEO IT | 1906
1.2.1.5.2 | Deploy learning to end-users | 10 days | 06 April 2026 11:36 | 20 April 2026 11:36 | 219 | 221 | Human Resources IN | 600
1.2.1.5.3 | Conduct deployment Go/No Go decision set | 5 days | 20 April 2026 11:36 | 27 April 2026 11:36 | 220 | 222 | Functional Professional IT;Functional Professional IN | 2060
1.2.1.5.4 | Execute production deployment | 4 days | 27 April 2026 11:36 | 01 May 2026 11:36 | 221 | 223 | Information Technology IN;Business Analyst IT;ERP Expert IT;ERP Professional IN | 3072
1.2.1.5.5 | Execute final data migration | 5 days | 01 May 2026 11:36 | 08 May 2026 11:36 | 222 | 225 | Business Analyst IT;ERP Expert IT;ERP Professional IN | 3540
1.2.1.6 | Run | 40 days | 08 May 2026 11:36 | 03 July 2026 11:36 |  |  |  | 22640
1.2.1.6.1 | Develop post implementation and evaluation reports | 10 days | 08 May 2026 11:36 | 22 May 2026 11:36 | 223 | 226 | Business Analyst IT;Information Technology IN | 3640
1.2.1.6.2 | Conduct service delivery transition | 10 days | 22 May 2026 11:36 | 05 June 2026 11:36 | 225 | 227 | Business Analyst IT;ERP Expert IT;ERP Professional IN;Information Technology IN | 7680
1.2.1.6.3 | Track value realization | 10 days | 05 June 2026 11:36 | 19 June 2026 11:36 | 226 | 228 | Business Analyst IT;Information Technology IN | 3640
1.2.1.6.4 | Close project | 10 days | 19 June 2026 11:36 | 03 July 2026 11:36 | 227 | 229 | Business Analyst IT;ERP Expert IT;ERP Professional IN;Information Technology IN | 7680
1.2.2 | Meeting with Stakeholders for project 2 closure | 1 day | 03 July 2026 11:36 | 06 July 2026 11:36 | 228 | 284 | CEO IN;CEO IT;Project Director | 2000
1.3 | Project3 | 374,25 days | 15 January 2025 09:38 | 23 June 2026 11:36 |  |  |  | 337752.28
1.3.1 | Initiation | 6 days | 15 January 2025 09:38 | 23 January 2025 09:38 |  |  |  | 7354.68
1.3.1.1 | Conduct SWOT analysis | 2 days | 15 January 2025 09:38 | 17 January 2025 09:38 | 80 | 233 | Business analyst | 2255.52
1.3.1.2 | Develop future scenarios | 2 days | 17 January 2025 09:38 | 21 January 2025 09:38 | 232 | 234 | Business analyst | 2255.52
1.3.1.3 | Communicate current threat to employees | 1 day | 21 January 2025 09:38 | 22 January 2025 09:38 | 233 | 235 | Business analyst | 1127.76
1.3.1.4 | Discussion with industry expert and stakeholders | 1 day | 22 January 2025 09:38 | 23 January 2025 09:38 | 234 | 237 | Business analyst[50%];CEO IT | 1715.88
1.3.2 | Building Guiding coalition | 8 days | 23 January 2025 09:38 | 04 February 2025 09:38 |  |  |  | 19160
1.3.2.1 | Choose the Sponsor | 2 days | 23 January 2025 09:38 | 27 January 2025 09:38 | 235 | 238 | CEO IT | 2304
1.3.2.2 | Choose the Senior Guiding Team | 2 days | 27 January 2025 09:38 | 29 January 2025 09:38 | 237 | 239 | Sponsor | 880
1.3.2.3 | Choose the Field Guiding Team | 2 days | 29 January 2025 09:38 | 31 January 2025 09:38 | 238 | 240 | Senior guiding team;Sponsor | 5320
1.3.2.4 | Choose the Change Team | 2 days | 31 January 2025 09:38 | 04 February 2025 09:38 | 239 | 242 | Field guiding team;Senior guiding team | 10656
1.3.3 | New strategic Vision Creation | 12 days | 04 February 2025 09:38 | 20 February 2025 09:38 |  |  |  | 65179.2
1.3.3.1 | Align vision with core values | 2 days | 04 February 2025 09:38 | 06 February 2025 09:38 | 240 | 243 | Change team;Senior guiding team | 10123.2
1.3.3.2 | Find and incorporate employees input | 3 days | 06 February 2025 09:38 | 11 February 2025 09:38 | 242 | 245 | Change team;Field guiding team | 17848.8
1.3.3.3 | Ensure clarity and communicability | 1 day | 11 February 2025 09:38 | 12 February 2025 09:38 |  |  |  | 5949.6
1.3.3.3.1 | Verify that the vision is easily understandable for everyone in the organization | 1 day | 11 February 2025 09:38 | 12 February 2025 09:38 | 243 | 247 | Change team;Field guiding team | 5949.6
1.3.3.4 | Ties Vision to data and evidence | 5 days | 12 February 2025 09:38 | 19 February 2025 09:38 |  |  |  | 25308
1.3.3.4.1 | Analyze forecast, market research and business trends to give evidence to the vision | 5 days | 12 February 2025 09:38 | 19 February 2025 09:38 | 245 | 249 | Change team;Senior guiding team | 25308
1.3.3.5 | Strive for Conciseness | 1 day | 19 February 2025 09:38 | 20 February 2025 09:38 |  |  |  | 5949.6
1.3.3.5.1 | Make sure the vision is coincident and can be explained in 5 minutes | 1 day | 19 February 2025 09:38 | 20 February 2025 09:38 | 247 | 252 | Change team;Field guiding team | 5949.6
1.3.4 | Communicating Vision change to the employees | 8 days | 20 February 2025 09:38 | 04 March 2025 09:38 |  |  |  | 23532
1.3.4.1 | Develop communication plan | 3 days | 20 February 2025 09:38 | 25 February 2025 09:38 |  |  |  | 9324
1.3.4.1.1 | Choose information to communicate | 2 days | 20 February 2025 09:38 | 24 February 2025 09:38 | 249 | 253 | Field guiding team | 6216
1.3.4.1.2 | Choose communication channels | 1 day | 24 February 2025 09:38 | 25 February 2025 09:38 | 252 | 254 | Field guiding team | 3108
1.3.4.2 | Applies the communication process | 5 days | 25 February 2025 09:38 | 04 March 2025 09:38 | 253 | 257 | Change team | 14208
1.3.5 | Removing barriers phase | 14 days | 06 April 2026 11:36 | 24 April 2026 11:36 |  |  |  | 42712.8
1.3.5.1 | Identify barriers to change | 6 days | 06 April 2026 11:36 | 14 April 2026 11:36 |  |  |  | 13320
1.3.5.1.1 | Identify inadequate process | 2 days | 06 April 2026 11:36 | 08 April 2026 11:36 | 254;219 | 258 | Senior guiding team | 4440
1.3.5.1.2 | Identify employees resistance | 1 day | 08 April 2026 11:36 | 09 April 2026 11:36 | 257 | 259 | Senior guiding team | 2220
1.3.5.1.3 | Identify misaligned organizational policies and structures | 2 days | 09 April 2026 11:36 | 13 April 2026 11:36 | 258 | 260 | Senior guiding team | 4440
1.3.5.1.4 | Identify disempowering management practices | 1 day | 13 April 2026 11:36 | 14 April 2026 11:36 | 259 | 261 | Senior guiding team | 2220
1.3.5.2 | Develop an action plan to remove barriers | 3 days | 14 April 2026 11:36 | 17 April 2026 11:36 | 260 | 262 | Senior guiding team;Change team | 15184.8
1.3.5.3 | Implement Changes | 5 days | 17 April 2026 11:36 | 24 April 2026 11:36 | 261 | 265 | Change team | 14208
1.3.6 | Chasing short win | 17 days | 24 April 2026 11:36 | 19 May 2026 11:36 |  |  |  | 55944
1.3.6.1 | Identify short-term win opportunities | 4 days | 24 April 2026 11:36 | 30 April 2026 11:36 |  |  |  | 8880
1.3.6.1.1 | Identify all the possible short term win opportunities | 3 days | 24 April 2026 11:36 | 29 April 2026 11:36 | 262 | 266 | Senior guiding team | 6660
1.3.6.1.2 | Identify all the pros and cons for each project | 1 day | 29 April 2026 11:36 | 30 April 2026 11:36 | 265 | 268 | Senior guiding team | 2220
1.3.6.2 | Pilot project phase | 13 days | 30 April 2026 11:36 | 19 May 2026 11:36 |  |  |  | 47064
1.3.6.2.1 | Select the pilot project to achive the short term win | 2 days | 30 April 2026 11:36 | 04 May 2026 11:36 | 266 | 269 | Senior guiding team | 4440
1.3.6.2.2 | Break down project into components | 2 days | 04 May 2026 11:36 | 06 May 2026 11:36 | 268 | 270 | Change team;Senior guiding team | 10123.2
1.3.6.2.3 | Define short term goals for each components | 3 days | 06 May 2026 11:36 | 11 May 2026 11:36 | 269 | 271 | Change team;Senior guiding team | 15184.8
1.3.6.2.4 | Implement the project | 5 days | 11 May 2026 11:36 | 18 May 2026 11:36 | 270 | 272 | Change team | 14208
1.3.6.2.5 | Celebrate short term win | 1 day | 18 May 2026 11:36 | 19 May 2026 11:36 | 271 | 274 | Field guiding team | 3108
1.3.7 | Scale up phase | 5 days | 19 May 2026 11:36 | 26 May 2026 11:36 |  |  |  | 25840.8
1.3.7.1 | Evaluate what worked and what needs improvments | 2 days | 19 May 2026 11:36 | 21 May 2026 11:36 | 272 | 275 | Field guiding team;Senior guiding team | 10656
1.3.7.2 | Identify and remove unnecessary processes and interdependencies | 3 days | 21 May 2026 11:36 | 26 May 2026 11:36 | 274 | 277 | Change team;Senior guiding team | 15184.8
1.3.8 | Institute change phase | 19 days | 26 May 2026 11:36 | 22 June 2026 11:36 |  |  |  | 94216.8
1.3.8.1 | Identify and incorporate norms and values that reinforce the change | 2 days | 26 May 2026 11:36 | 28 May 2026 11:36 | 275 | 278 | Change team;Senior guiding team | 10123.2
1.3.8.2 | communicate these values to HR and the hiring team | 1 day | 28 May 2026 11:36 | 29 May 2026 11:36 | 277 | 279 | Field guiding team | 3108
1.3.8.3 | Create new training and development programs to help employees develop skills and competencies relevant to the new changes | 10 days | 29 May 2026 11:36 | 12 June 2026 11:36 | 278 | 280 | Change team;Senior guiding team | 50616
1.3.8.4 | Detect process that do not align with the new culture | 3 days | 12 June 2026 11:36 | 17 June 2026 11:36 | 279 | 281 | Change team;Senior guiding team | 15184.8
1.3.8.5 | Eliminate or renew each process | 3 days | 17 June 2026 11:36 | 22 June 2026 11:36 | 280 | 282 | Change team;Senior guiding team | 15184.8
1.3.9 | Meeting with stakeholders for project 3 closure | 1 day | 22 June 2026 11:36 | 23 June 2026 11:36 | 281 | 284 | CEO IT;Sponsor;Senior guiding team | 3812
1.4 | FINAL MEETING | 1 day | 06 July 2026 11:36 | 07 July 2026 11:36 |  |  |  | 1536
1.4.1 | Final meeting | 1 day | 06 July 2026 11:36 | 07 July 2026 11:36 | 183;229;282;14 |  | CEO IN;CEO IT | 1536

## Resource_Table1
WBS | Initials | Max_Units | Standard_Rate
Team of Italian workers (4 workers each) | TI | 900% | 320,00 €/h
Team of Indian workers (4 workers each) | TB | 900% | 65,00 €/h
Italian Project Engineer | IPE | 200% | 140,00 €/h
Italian Specialized Engineer | ISE | 400% | 120,00 €/h
Indian Project Engineer | BPE | 200% | 70,00 €/h
Indian Specialized Engineer | BSE | 400% | 60,00 €/h
Purchasing agent | P | 400% | 70,00 €/h
Crashing Team Indian workers | CT-IN | 300% | 130,00 €/h
Crashing Team Italian workers | CT-IT | 300% | 640,00 €/h
Owner | O | 300% | 0,00 €/h
Transportation Company | T
Supplier | S
CEO IT | CI | 100% | 144,00 €/h
Functional Manager IT | FMI | 100% | 57,00 €/h
Functional Professional IT | FPI | 100% | 44,00 €/h
CEO IN | CB | 100% | 48,00 €/h
Functional Manager IN | FMB | 100% | 11,00 €/h
Functional Professional IN | FPB | 100% | 7,50 €/h
Human Resources IN | H | 100% | 7,50 €/h
Information Technology IN | I | 100% | 7,50 €/h
Project Director | PD | 100% | 58,00 €/h
ERP Expert IT | EI | 100% | 43,00 €/h
Business Analyst IT | BAI | 100% | 38,00 €/h
ERP Professional IN | EB | 100% | 7,50 €/h
Sponsor | SP | 100% | 55,00 €/h
Senior guiding team | SGT | 100% | 277,50 €/h
Field guiding team | F | 100% | 388,50 €/h
Change team | C | 100% | 355,20 €/h
Business analyst | B | 100% | 140,97 €/h
Crashing italian project engineering | CIPE | 100% | 280,00 €/h
Crashing italian specialized engineering | CISE | 100% | 240,00 €/h
Crashing indian project engineering | CBPE | 100% | 140,00 €/h
Crashing indian specialized engineering | CBSE | 100% | 120,00 €/h