## Sheet1
|  | ct1 | ct2 | ct3 | ct4 | ct5 | ct6 | ct7 | ct8 | ct9 | ct10 | ct11 | ct12 | ct13 | ct14 | ct15 | ct16 | ct17 | ct18
|  | Final washing station | Installation | FINAL LINE TESTING | ERP Implementation | Test | Deploy | Meeting to start project 3 | Deploy learning to end-users | Conduct deployment Go/No Go decision set | Execute production deployment | Execute final data migration | Run | Develop post implementation and evaluation reports | Conduct service delivery transition | Track value realization | Close project | Meeting with Stakeholders for project 2 closure | FINAL MEETING
r1 | New environmental rule | bar: ct1
r2 | New foreign investment rule | bar: ct4
r3 | Change in economic condition | bar: ct15
r4 | Monsoon
r5 | Extreme temperature
r6 | Technological obsolescence | bar: ct2 to ct6; ct8 to ct14
r7 | Supply Chain Disruption | bar: ct1; ct5 to ct6; ct8; ct10 to ct12; ct14
r8 | Labor Shortages | bar: ct2
r9 | Political Instability | bar: ct7; ct9; ct16 to ct18
r10 | Regulatory Delays | bar: ct3 to ct4; ct9; ct13
TOP 10 RISKS
1) New environmental rule
2) New foreign investment rule
3) Change in economic condition
4) Monsoon
5) Extreme temperature
6) Technological obsolescence
7) Supply Chain Disruption
8) Labor Shortages
9) Political Instability
10) Regulatory Delay

## Sheet2
RISKS | direct | indirect
New Environmental Rule | Increased compliance expenses | Project delays result in additional labor costs
New Foreign Investment Rule | Legal expenses for compliance | Potential delays in investment
Change in economic condition | Increased material costs | Project delays due to financial constraints
Monsoon | Potential damage to materials | Project delays due to weather disruptions
Extreme temperature | Specialized equipment for extreme temperatures | Potential delays in production
Technological obsolescence | Upgrading technology | Potential delays in production
Supply Chain Disruption | Finding alternative suppliers | Project delays due to supply chain disruption
Labor Shortages | Hiring temporary or specialized labor | Potential project delays
Political Instability | Increased security measures | Project delays due to political unrest
Regulatory Delay | Legal expenses for navigating regulatory changes | Project delays due to regulatory hurdles

## Sheet3
1. POLITICAL:
Stability and changes in the Indian government can impact project regulations and approvals. The next Indian general elections will take place between April and May 2024 but the leadership of the current president Narendra Modi does not seem to be in question, so from a political point of view no upheavals are expected.
2. ECONOMIC:
Exchange rate fluctuations between the rupee and the dollar could affect the cost of imported goods and services.
One of the most important factor that could impact on the exchange rate is the Inflation: the latter tends to be inversely related to any currency’s strength, indeed the higher the inflation, the weaker will be the country’s currency. Currently, as we are witnessing a period of rising inflation in India, the purchasing power of rupee is going down. Thus, we can see the rupee weakening against the dollar.
Another important factor that could impact on the exchange rate is the interest rate. In times of escalating inflation, central banks often respond by implementing interest rate hikes to mitigate inflationary pressures. The increase in interest rates tends to make the country more appealing to foreign investors, thereby strengthening the local currency. The RBI Repurchase Rate ended 2022 at 6.50%, up from the 4.00% end-2021, highlighting a tendency towards a rapid increase in interest rates.
3. SOCIOLOGICAL:
The project involves team members from both India and Italy. Varied cultural norms, communication styles, and work practices may lead to misunderstandings or challenges in team collaboration. It's essential that both of the companies implement cultural sensitivity training and effective communication strategies to bridge these gaps, before the start of the project.
4. TECHNOLOGICAL:
Rapid technological changes may necessitate updates or changes to the project and
dependence on specific technologies may introduce risks related to obsolescence. This is not the case for the project analyzed as the construction techniques of the plant will not vary during the life of the project, nor will the techniques for manufacturing the pieces produced by the joint venture.
5. LEGAL:
Given that the project will be carried out by a joint venture composed partly of Indian teams, rigorous conduct in compliance with local laws is expected, as the local lawyers of the Indian company can be used if necessary.
6. ENVIRONMENTAL:
Compliance with stringent environmental regulations, particularly regarding waste disposal and emissions, is crucial for legal adherence. The project must also account for climate-related challenges, such as monsoons and extreme temperatures, implementing strategies to mitigate potential risks. Aligning with India's emphasis on sustainability, incorporating eco-friendly practices and obtaining Environmental Impact Assessment (EIA) approvals are vital. Additionally, assessing the project's impact on biodiversity, engaging in community
initiatives, and exploring opportunities for renewable energy integration contribute to a holistic approach. Successful navigation of these environmental considerations not only ensures regulatory compliance but also fosters positive relationships with local communities and stakeholders, ultimately enhancing the project's overall sustainability and success

## risk assesment
WBS | task | risk | probobility | impact | cost | risk exposure | risk order | Accept / mitigate / transfer | how? | Mitigation Cost | Cost after management
1.1.6 | ON SITE ERECTION PHASE | New Environmental Rule | 3 | 4 | 4359600 | 52315200 | 12 | Mitigate | Implementing an advanced waste disposal system | 100000 | 4259600
1.1.6.5 | OP.50 | Change in Economic Condition | 3 | 3 | 370800 | 3337200 | 9 | Mitigate | Implementing cost-saving measures | 50000 | 320800
1.1.6.5.1 | Double-spindle CNC machine 5 | Technological Obsolescence | 4 | 3 | 123600 | 493200 | 12 | Mitigate | Regular technology updates, vendor support | 30000 | 93600
1.1.6.5.1.1 | Installation | Technological Obsolescence | 3 | 4 | 46800 | 140400 | 12 | Accept | Monitor technology trends, plan for updates | _ | 46800
1.1.6.5.1.1 | Installation | Labor Shortages | 2 | 3 | 46800 | 93600 | 6 | Mitigate | Cross-train employees, explore additional labor sources | 20000 | 26800
1.1.6.5.3 | Single-spindle CNC machine 3 | Technological Obsolescence | 3 | 3 | 123600 | 370800 | 9 | Accept | Regularly update technology, agile development | _ | 123600
1.1.6.5.3 | Single-spindle CNC machine 3 | Supply Chain Disruption | 3 | 3 | 123600 | 370800 | 9 | Mitigate | Diversify suppliers, establish contingency plans | 50000 | 73600
1.1.6.10.1 | Final Washing Station | New Environmental Rule | 3 | 4 | 441000 | 5292000 | 12 | Mitigate | Implementing an advanced waste disposal system | 100000 | 341000
1.1.6.10.1 | Final Washing Station | Supply Chain Disruption | 4 | 4 | 441000 | 7056000 | 16 | Mitigate | Diversify suppliers, establish backup plans | 150000 | 591000
1.1.6.10.1 | Installation | Technological Obsolescence | 3 | 4 | 210600 | 2527200 | 12 | Accept | Monitor technology trends, plan for updates | _ | 2527200
1.1.6.10.1 | Installation | Labor Shortages | 2 | 3 | 210600 | 631800 | 6 | Mitigate | Cross-train employees, explore additional labor sources | 80000 | 290600
1.1.7 | Final Line Testing | Technological Obsolescence | 3 | 3 | 73600 | 220800 | 9 | Accept | Regularly update testing equipment | _ | 220800
1.1.7 | Final Line Testing | Regulatory Delays | 2 | 3 | 73600 | 220800 | 6 | Accept | Proactive engagement with regulatory authorities | _ | 220800
1.2.1 | ERP Implementation | New Foreign Investment Rule | 3 | 4 | 205682 | 2468184 | 12 | Mitigate | Legal consultation, compliance strategies | 80000 | 2348184
1.2.1 | ERP Implementation | Technological Obsolescence | 4 | 4 | 205682 | 3288512 | 16 | Accept | Continuous technology monitoring, agile development | _ | 3288512
1.2.1 | ERP Implementation | Regulatory Delays | 2 | 3 | 205682 | 617046 | 6 | Transfer | Purchase insurance to cover regulatory delays | 50000 | 567046
1.2.1.4 | Test | Technological Obsolescence | 3 | 3 | 19224 | 57672 | 9 | Accept | Regular technology updates, testing protocols | _ | 57672
1.2.1.4 | Test | Supply Chain Disruption | 3 | 3 | 19224 | 57672 | 9 | Mitigate | Diversify suppliers, establish contingency plans | 30000 | 27672
1.2.1.5 | Deploy | Technological Obsolescence | 3 | 3 | 11178 | 33534 | 9 | Accept | Regular technology updates, agile deployment | 20000 | 33534
1.2.1.5 | Deploy | Supply Chain Disruption | 3 | 3 | 11178 | 33534 | 9 | Mitigate | Diversify suppliers, establish contingency plans | 15000 | 13534
1.2.1.5.1 | Meeting to Start Project 3 | Political Instability | 4 | 4 | 1906 | 30496 | 16 | Mitigate | Political risk analysis, diplomatic relations | _ | 16906
1.2.1.5.2 | Deploy Learning to End-Users | Technological Obsolescence | 3 | 3 | 600 | 1800 | 9 | Accept | Regular technology updates, user training protocols | 5000 | 1800
1.2.1.5.2 | Deploy Learning to End-Users | Supply Chain Disruption | 3 | 3 | 600 | 1800 | 9 | Mitigate | Diversify suppliers, establish contingency plans | _ | 800
1.2.1.5.3 | Conduct Deployment Go/No Go Decision | Political Instability | 4 | 4 | 2060 | 32960 | 16 | Mitigate | Political risk analysis, diplomatic relations | 10000 | 22960
1.2.1.5.3 | Conduct Deployment Go/No Go Decision | Regulatory Delays | 3 | 3 | 2060 | 18540 | 9 | Accept | Proactive engagement with regulatory authorities | _ | 18540
1.2.1.5.3 | Conduct Deployment Go/No Go Decision | Technological Obsolescence | 3 | 3 | 2060 | 18540 | 9 | Accept | Regular technology updates, agile deployment | _ | 18540
1.2.1.5.3 | Conduct Deployment Go/No Go Decision | Supply Chain Disruption | 3 | 3 | 2060 | 18540 | 9 | Mitigate | Diversify suppliers, establish contingency plans | 15000 | 3540
1.2.1.5.4 | Execute Production Deployment | Technological Obsolescence | 3 | 3 | 3072 | 9216 | 9 | Accept | Regular technology updates, agile deployment | _ | 9216
1.2.1.5.4 | Execute Production Deployment | Supply Chain Disruption | 3 | 3 | 3072 | 9216 | 9 | Mitigate | Diversify suppliers, establish contingency plans | 10000 | _
1.2.1.5.5 | Execute Final Data Migration | Technological | 4 | 3 |  |  | 12
1.2.1.6 | Run | Technological Obsolescence | 3 | 2 | 22640 | 45280 | 6 | Accept |  | _ | 22640
1.2.1.6.1 | Develop post-implementation and evaluation reports | Regulatory Delays | 2 | 3 | 3640 | 21840 | 6 | Mitigate | Proactive engagement with regulatory authorities | 5000 | -1360
1.2.1.6.2 | Conduct service delivery transition | Regulatory Delays | 3 | 3 | 7680 | 69120 | 9 | Mitigate | Proactive engagement with regulatory authorities | 10000 | -2320
1.2.1.6.3 | Track value realization | Change in Economic Condition | 4 | 3 | 3640 | 43680 | 12 | Mitigate | Continuous monitoring of economic conditions | 5000 | -1360
1.2.1.6.4 | Close project | Change in Economic Condition | 4 | 3 | 7680 | 91800 | 12 | Mitigate | Continuous monitoring of economic conditions | 8000 | -320
1.2.2 | Meeting with Stakeholders for project 2 closure | Political Instability | 4 | 4 | 2000 | 32000 | 16 | Mitigate | Political risk analysis, diplomatic relations | 15000 | -13000
1.4 | FINAL MEETING | Political Instability | 4 | 4 | 1536 | 24576 | 16 | Mitigate | Political risk analysis, diplomatic relations | 10000 | -8464